## Slide 1: Production progress report FTM DECEMBER 23.

## Slide 2: In House Labour Monthly Summary
Sr No | Month | Labour Cost | Concrete | Avg Cost/Cum
1. | April 22 | 2429680.2 | 543.72 | 4468.623942
2. | May 22 | 2471216.7 | 652.44 | 3787.653629
3. | June 22 | 2813211.5 | 662.05 | 4249.243305
4. | July 22 | 2655187.5 | 400.03 | 6637.47094
5. | August 22 | 2564097.2 | 445.05 | 5761.368783
6. | September 22 | 1990611.5 | 285.44 | 6973.834985
7. | October 22 | 2060881 | 386.6 | 5330.783756
8. | November 22 | 2662365 | 554.5425 | 4801.011645
9. | December 22 | 3995349.8 | 935.449 | 4268.789227
10. | January 23 | 4793114.919 | 971.5238 | 4933.605248
11. | February 23 | 5192192 | 2232.18 | 2326.0633
12. | March 23 | 4288932 | 903.2691 | 4748.232835
13. | April 23 | 5262161.03 | 824.24 | 6384.3
14. | May 23 | 5668339.00 | 1005.79 | 5635.70824
15. | June 23 | 7201632.00 | 1085.3411 | 6635.362836
16. | July 23 | 4682900.0 | 506.18 | 9251.45
17. | AUGUST 23 | 7961810.00 | 1315.51 | 6052.26

## Slide 3
Sr No | Month | Labour Cost | Concrete | Avg Cost/Cum
17. | AUGUST 23 | 7961810.00 | 1315.51 | 6052.26
18. | SEPTEMBER 23 | 10003410.00 | 1562.67 | 6401.48
19. | OCTOBER 23 | 10370522.4 | 1342.31 | 7725.89
20. | NOVEMBER 23 | 8979300.9 | 1195.89 | 7508.44
21. | DECEMBER 23 | 13128945.3 | 1862.61 | 7048.66
In House Labour Monthly Summary

## Slide 4: Special Mould Area. Person in charge – MR. Arbab
Sr No | Elements | Total Elements to be casted | Planned FTM December 23 | Concrete FTM December 23 | Achieved FTM December 23 | Concrete Consumed | Unplanned Element | Unplanned Concrete | Produced Element | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM December 23
1. | PW | 3129 | 219 | 631.95 | 73 | 161.92 | 0 | 0 | 1093 | 2036 | 73 | 225.77 |  | 
2. | PSS | 5862 | 260 | 88.342 | 290 | 99.01 | 30 | 10.668 | 3916 | 1946 | 14 | 6.9 |  | 
3. | PB | 2806 | 193 | 73.1 | 79 | 20.22 | 0 | 0 | 2156 | 650 | 155 | 70.66 |  | 
4. | COUNTER WEIGHT |  |  |  |  |  | 5 | 5 |  |  |  |  |  | 
5. | LAN | 920 | 114 | 106.4 | 52 | 49.40 | 0 | 0 | 494 | 426 | 15 | 14.25 |  | 
TOTAL |  | 11889 | 786 | 899.792 | 494 | 330.56 | 35 | 15.668 | 7659 | 5058 | 257 | 317.58 | 1800 | 4398.32

## Slide 5: Pod Production Person in charge – MR. Rahil
Sr No | Elements | Total Elements to be casted | Plan FTM December 23 | Concrete FTM December 23 | Achieved FTM December 23 | Concrete Consumed | Unplanned Element | Unplanned Concrete | Produced Element | Balance to cast | Plan For Next Month | Concrete Consumption for next month | Approved Cost/CMT | Cost/CMT FTM December 23
1. | UT Kitchen POD - 1 | 217 | 2 | 15.12 |  |  |  |  | 180 | 37 | 11 | 83.16 |  | 
2. | UT Kitchen POD - 2 | 453 | 1 | 7.56 |  |  |  |  | 194 | 259 | 44 | 332.64 |  | 
3. | Lift POD | 92 | 14 | 105.84 |  |  |  |  | 35 | 57 |  |  |  | 
4. | LTKP - 1 | 60 | 60 | 453.6 | 24 | 181.44 |  |  | 47 | 13 | 12 | 90.72 |  | 
5. | LTKP - 2 | 60 | 50 | 378 | 26 | 196.56 |  |  | 60 | 00 |  |  |  | 
6. | LTKP – 3 | 30 | 34 | 257.04 | 15 | 113.4 |  |  | 25 | 5 | 6 | 45.36 |  | 
7. | LTKP - 4 | 30 | 64 | 483.84 | 27 | 204.12 |  |  | 30 | 00 |  |  |  | 
8. | RKP - 1 | 12 | 10 | 75.6 | 8 | 60.48 |  |  | 4 | 0 |  |  |  | 
9. | MTKP - 1 | 12 |  |  |  |  |  |  |  |  | 10 | 75.6 |  | 
10. | MTKP - 2 | 12 | 6 | 45.36 | 3 | 22.68 |  |  | 3 | 9 | 6 | 45.36 |  | 

## Slide 6
Sr No | Elements | Total Elements to be casted | Plan FTM December 23 | Concrete FTM December 23 | Achieved FTM December 23 | Concrete Consumed | Unplanned Element | Unplanned Concrete | Produced Element | Balance to cast | Plan For Next Month | Concrete Consumption for next month | Approved Cost/CMT | Cost/CMT FTM December 23
11. | MTKP - 3 | 6 | 2 | 15.12 |  |  |  |  | 6 | 0 | 6 | 45.36 |  | 
12. | MTKP - 4 | 6 | 8 | 60.48 |  |  |  |  |  |  | 1 | 7.56 |  | 
13. | Kitchen POD – 101/102/103/104 | 140 | 79 | 698.36 | 12 | 106.08 |  |  | 25 | 1115 | 87 | 769.08 |  | 
14. | Lift POD 101/102/103/104 | 176 | 5 | 0 |  |  |  |  |  | 176 | 34 | 0 |  | 
15. | Kitchen pod FKP-01/02 | 72 | 10 | 64 |  |  |  |  | 36 | 36 |  |  |  | 
16. | Kitchen pod FKP-101/102 | 28 | 71 | 454.82 | 17 | 108.8 |  |  | 17 | 11 | 11 | 70.6 |  | 
TOTAL |  | 1406 | 416 | 3114.74 | 132 | 993.56 | 00 | 00 | 662 | 1718 | 228 | 1565.44 | 2200 | 3754.08

## Slide 7: Precast Factory STP Tank Work Person In charge – MR. Gauri.
Sr No | Description | UoM | Qty | Cost/CMT FTM December 23
1. | STP TANK WORK | CMT | 4 | 1907.66

## Slide 8: Element Repairing Person In charge – MR. Sivaraman.
Sr No | Element/Description | Planned FTM December 23 | Achieved FTM December 23 | Plan For Next Month | Approved Cost/CMT | Cost/CMT FTM December 23 | Remarks
1. | Element Handover | 00 | 191 | 00 | 500 | 972.02 | 
Element Repairing Person In charge – MR. Amardeep
Sr No | Element/Description | Planned FTM December 23 | Achieved FTM December 23 | Plan For Next Month | Approved Cost/CMT | Cost/CMT FTM December 23 | Remarks
1. | Element Handover | 00 | 151 | 00 | 500 | 1146.48 | 

## Slide 9: Reinforcement Yard Person In charge – MR. DK Patel.
Sr No | Element/Description | Planned FTM November 23 | Achieved FTM November 23 | Plan For Next Month | Approved Cost/KG | Cost/KG, MTT FTM December 23 | Remarks
1. | Reinforcement | 853.11 MTT | 252.56 MTT | 332.38MTT | 15 | 11.14 | 

## Slide 10
POD FINISHING Person In charge – MR. SIVARAMAN.
Sr No | Element/Description | Planned FTM November 23 | Achieved FTM December 23 | Plan For Next Month | Approved Cost/CUM | Cost/CUM FTM December 23 | Remarks
1. | Element Handover | 80 | 96 | 120 | 1050 | 2158.23 | 

## Slide 11
Carousal Factory Person In charge – MR. AMARDEEP
Sr No | Elements | Total Elements to be casted | Planned FTM December 23 | Concrete FTM December 23 | Achieved FTM December 23 | Concrete Consumed | Unplanned Element | Unplanned Element | Produced Element | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM December 23
1. | NLW | 23034 | 2525 | 1126.54 | 329 | 154.80 | 00 | 00 | 9996 | 13038 | 1213 | 482.28 |  | 
2. | LS | 10500 | 405 | 45.501 | 305 | 32.21 | 00 | 00 | 6134 | 4366 | 78 | 13.59 |  | 
3. | PW | 3129 | 309 | 429.92 | 124 | 174.79 | 00 | 00 | 1312 | 1817 | 165 | 302..89 |  | 
4. | LAN | 920 | 68 | 34.52 | 12 | 6.12 | 00 | 00 | 494 | 426 | 6 | 3.06 |  | 
5. | PSS | 5862 | 54 | 34.59 | 6 | 3.53 | 00 | 00 | 3916 | 1946 | 4 | 2.48 |  | 
6. | TRENCH SLAB |  |  |  |  |  | 8 | 2.70 |  |  |  |  |  | 
7. | RECAST ELEMENT |  |  |  |  |  | 78 | 3.51 |  |  |  |  |  | 
TOTAL |  |  | 3369 | 1671.07 | 776 | 371.45 | 86 | 6.21 | 21852 | 21593 | 1466 | 804.3 | 1800 | 6918.80

## Slide 12
Sr No | Elements | Total Elements to be casted | Planned FTM December 23 | Concrete FTM December 23 | Achieved FTM December 23 | Concrete Consumed | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM December 23
1. | HCS |  | 35.4 BED | 636.16 | 11 BED | 155.84 |  | 11.1 BED | 197.80 |  | 3262.04
HCS Factory Person In charge – MR. RANA

## Slide 13
Sr No | Element/Description | Planned FTM December 23 | Achieved FTM December 23 | Plan For Next Month | Approved Cost/KGS | Cost/CMT FTM December 23 | Remarks
1. | STEEL FABRICATION | 00 | 13.74MTT | 00 | 00 | 20.42 | 
FABRICATION Person In charge – MR. Ramdhyan Yadav

## Slide 14
BUILDING ERECTION WORK Person In charge – MR. SATISH KUMAR
Sr No | Element/Description | Planned FTM December 23 | Achieved FTM December 23 | Plan For Next Month | Remarks
1. | ERECTION BUILDING 18 | F4 TO F6 | F4 TO F6 | F7 TO F10 | 
2. | ERECTION BUILDING 19 |  | F1 |  | F1 SCREED PENDING

## Slide 15: Special Mould & Pod Factory & Other work Concrete Monthly Summary
Sr No | Grade | Unit | Theoretical Concrete (Element) | Cover Drain and other activities | Total Theoretical | Actual OLD RMC Concrete | Actual HCS RMC Concrete | POD BATCHING PLANT | Concrete Rejected | TOTAL OLD RMC & HCS RMC & POD RMC ACTUAL CONCRETE | Difference (Actual – Theoretical) | Difference %
1. | M10 | CUM | 0 | 4 | 4 | 4 | - | - | 00 | 4 | - | -
2. | M30 | CUM | 0 | 00 | 00 | 00 |  | - | 00 | 00 | - | -
3. | M40 | CUM | 168.64 | 5.3 | 173.67 | 00 | 187.6 | - | 00 | 187.6 | 13.93 | 8.02
4. | M65 | CUM | 1155.48 | 00 | 1155.48 | 4.5 | 257.23 | 1000.20 | 7.70 | 1254.23 | 98.75 | 8.54
TOTAL |  | CUM | 1324.12 | 9.3 | 1333.15 | 9.5 | 444.83 | 1000.20 | 7.70 | 1445.83 | 112.68 | 8.45

## Slide 16
Sr No | Grade | Unit | Theoretical Concrete (Element) | Other Work concrete | Total Theoretical Concrete | Reject Concrete | Total Actual Concrete | Difference (Actual – Theoretical) | Difference %
1. | M20 | CUM | 100.50 |  | 100.50 | 00 | 109.25 | 8.75 | 8.71
2. | M40 | CUM | 96.16 | 6.21 | 102.37 | 00 | 100.45 | -1.92 | -1.88
3. | M65 | CUM | 174.79 |  | 174.79 | 00 | 183.21 | 8.42 | 4.81
TOTAL |  | CUM |  |  | 377.66 | 00 | 392.91 | 15.25 | 4.04
Carousal Concrete Monthly Summary

## Slide 17
HCS Concrete Monthly Summary
Sr No | Grade | Unit | Theoretical Concrete (Element) | Reject Concrete | Actual Concrete | Total actual Concrete | Difference (Actual – Theoretical | Difference %
1. | M60 | CUM | 155.84 |  | 163.5 | 163.5 | 7.66 | 4.91
TOTAL |  | CUM |  |  | 163.5 | 163.5 | 7.66 | 4.91