## Slide 1: Production progress report FTM FEBRUARY 24.

## Slide 2: In House Labour Monthly Summary
Sr No | Month | Labour Cost | Concrete | Avg Cost/Cum
1. | April 22 | 2429680.2 | 543.72 | 4468.623942
2. | May 22 | 2471216.7 | 652.44 | 3787.653629
3. | June 22 | 2813211.5 | 662.05 | 4249.243305
4. | July 22 | 2655187.5 | 400.03 | 6637.47094
5. | August 22 | 2564097.2 | 445.05 | 5761.368783
6. | September 22 | 1990611.5 | 285.44 | 6973.834985
7. | October 22 | 2060881 | 386.6 | 5330.783756
8. | November 22 | 2662365 | 554.5425 | 4801.011645
9. | December 22 | 3995349.8 | 935.449 | 4268.789227
10. | January 23 | 4793114.919 | 971.5238 | 4933.605248
11. | February 23 | 5192192 | 2232.18 | 2326.0633
12. | March 23 | 4288932 | 903.2691 | 4748.232835
13. | April 23 | 5262161.03 | 824.24 | 6384.3
14. | May 23 | 5668339.00 | 1005.79 | 5635.70824
15. | June 23 | 7201632.00 | 1085.3411 | 6635.362836
16. | July 23 | 4682900.0 | 506.18 | 9251.45
17. | AUGUST 23 | 7961810.00 | 1315.51 | 6052.26

## Slide 3
Sr No | Month | Labour Cost | Concrete | Avg Cost/Cum
17. | AUGUST 23 | 7961810.00 | 1315.51 | 6052.26
18. | SEPTEMBER 23 | 10003410.00 | 1562.67 | 6401.48
19. | OCTOBER 23 | 10370522.4 | 1342.31 | 7725.89
20. | NOVEMBER 23 | 8979300.9 | 1195.89 | 7508.44
21. | DECEMBER 23 | 13128945.3 | 1862.61 | 7048.66
22. | JANUARY 24 | 18989157.59 | 3224.04 | 5889.87
23. | February 24 | 21732401.83 | 3589.25 | 6054.86
In House Labour Monthly Summary

## Slide 4: Special Mould Area. Person in charge – MR. VITRANG
Sr No | Elements | Total Elements to be casted | Planned FTM February 24 | Concrete FTM February 24 | Achieved FTM February 24 | Concrete Consumed | Unplanned Element | Unplanned Concrete | Produced Element | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM February 24
1. | PW | 3129 | 109 | 331.81 | 79 | 152.33 |  |  | 1565 | 1564 | 57 | 213.76 |  | 
2. | PSS | 5862 | 68 | 17.98 | 113 | 31.43 | 45 | 13.45 | 4219 | 1643 | 15 | 3.02 |  | 
3. | PB | 4761 | 321 | 143.46 | 386 | 165.17 | 65 | 21.71 | 2837 | 1924 | 224 | 102.35 |  | 
4. | COUNTER WEIGHT & MANHOLE |  |  |  |  |  | 3 | 1.5 |  |  |  |  |  | 
5. | LAN | 920 | 52 | 49.4 | 67 | 63.65 |  |  | 639 | 281 | 24 | 22.8 |  | 
TOTAL |  | 14672 | 550 | 542.65 | 645 | 412.58 | 113 | 36.66 | 9260 | 5412 | 320 | 341.936 | 1800 | 4881.42

## Slide 5: Pod Production Person in charge – MR. Rahil
Sr No | Elements | Total Elements to be casted | Plan FTM February 24 | Concrete FTM February 24 | Achieved FTM February 24 | Concrete Consumed | Unplanned Element | Unplanned Concrete | Produced Element | Balance to cast | Plan For Next Month | Concrete Consumption for next month | Approved Cost/CMT | Cost/CMT FTM February 24
1. | UT Kitchen POD - 1 | 479 | 53 | 402.8 | 64 | 484.32 | 11 | 81.52 | 273 | 206 | 15 | 114 |  | 
2. | UT Kitchen POD - 2 | 453 | 57 | 433.2 | 67 | 506.96 | 10 | 73.76 | 303 | 150 | 13 | 98.8 |  | 
3. | Lift POD | 92 | 15 | 74.55 | 18 | 89.46 | 3 | 14.91 | 65 | 27 |  | 0 |  | 
4. | LTKP - 1 | 60 | 10 | 76 |  |  |  |  | 60 | 0 | 1 | 7.6 |  | 
5. | LTKP - 2 | 60 | 2 | 15.2 |  |  |  |  | 60 | 0 |  | 0 |  | 
6. | LTKP – 3 | 30 | 3 | 22.8 |  |  |  |  | 30 | 0 |  | 0 |  | 
7. | LTKP - 4 | 30 | 0 |  |  |  |  |  | 30 | 0 |  | 0 |  | 
8. | RKP - 1 | 12 | 2 | 7.6 |  |  |  |  | 4 | 0 |  | 0 |  | 
9. | RKP - 2 | 8 | 1 | 7.6 |  |  |  |  | 0 | 0 |  | 0 |  | 
10. | MTKP - 1 | 12 | 12 | 91.2 |  |  |  |  | 0 | 0 | 3 | 22.8 |  | 
11. | MTKP - 2 | 12 | 3 | 22.8 |  |  |  |  | 14 | -2 |  | 0 |  | 

## Slide 6
Sr No | Elements | Total Elements to be casted | Plan FTM February 24 | Concrete FTM February 24 | Achieved FTM February 24 | Concrete Consumed | Unplanned Element | Unplanned Concrete | Produced Element | Balance to cast | Plan For Next Month | Concrete Consumption for next month | Approved Cost/CMT | Cost/CMT FTM February 24
12. | MTKP - 3 | 6 | 9 | 45.6 |  |  |  |  | 7 | 0 |  | 0 |  | 
13. | MTKP - 4 | 6 | 6 | 45.6 |  |  |  |  | 6 | 0 |  | 0 |  | 
14. | Kitchen POD – 101/102/103/104 | 140 | 124 | 1104.84 | 42 | 371.84 |  |  | 86 | 54 | 242 | 2156.22 |  | 
15. | Lift POD 101/102/103/104 | 176 | 38 | 216.6 | 31 | 166.14 |  |  | 35 | 141 | 6 | 34.2 |  | 
15. | Kitchen pod FKP-01/02 | 72 |  |  |  |  |  |  | 36 | 36 |  | 0 |  | 
17. | Kitchen pod FKP-101/102 | 92 |  |  | 49 | 318.5 | 49 | 318.5 | 107 | -15 |  | 0 |  | 
TOTAL |  | 1478 | 335 | 2566.39 | 271 | 1937.22 | 73 | 488.69 | 1116 | 597 | 280 | 2433.62 | 2200 | 4295.01

## Slide 7: CIVIL Work Person In charge – MR. Gauri.
Sr No | Description | UoM | Qty | Cost/CMT FTM February 24
1. | CIVIL WORK | CMT | 64.8 | 2279.91

## Slide 8: Element Repairing Person In charge – MR. Sivaraman.
Sr No | Element/Description | Planned FTM February 24 | Achieved FTM February 24 | Plan For Next Month | Approved Cost/CMT | Cost/CMT FTM February 24 | Remarks
1. | Element Handover | 00 | 546 | 00 | 500 | 1295.50 | 
Element Repairing Person In charge – MR. Vitrang
Sr No | Element/Description | Planned FTM February 24 | Achieved FTM February 24 | Plan For Next Month | Approved Cost/CMT | Cost/CMT FTM February 24 | Remarks
1. | Element Handover | 00 | 274 | 00 | 500 | 1571.11 | 

## Slide 9: Reinforcement Yard Person In charge – MR. DK Patel.
Sr No | Element/Description | Planned FTM February 24 | Achieved FTM February 24 | Plan For Next Month | Approved Cost/KG | Cost/KG, MTT FTM February 24 | Remarks
1. | Reinforcement | 571.88 MTT | 398.106MTT | 375.57MTT | 15 | 11.49 | 
2. | AWM MACHINE |  | 38.681 MTT |  |  |  | 

## Slide 10
POD FINISHING Person In charge – MR. SIVARAMAN.
Sr No | Element/Description | Planned FTM February24 | Achieved FTM February24 | Plan For Next Month | Approved Cost/CUM | Cost/CUM FTM February24 | Remarks
1. | Element Handover | 120 | 02 | 00 | 1050 | 2067.33 | 
Sr No | Element/Description | Planned FTM February24 | Achieved FTM February24 | Plan For Next Month | Approved Cost/CUM | Cost/CUM FTM February24 | Remarks
1. | Element Handover |  | 224 | 00 |  | 8283.91 | 
POD ERECTION Person In charge – MR. SIVARAMAN.

## Slide 11
Carousal Factory Person In charge – MR. VITRANG
Sr No | Elements | Total Elements to be casted | Planned FTM February 24 | Concrete FTM February 24 | Achieved FTM February 24 | Concrete Consumed | Unplanned Element | Unplanned Element | Produced Element | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM February 24
1. | NLW | 23034 | 1887 | 757.98 | 1541 | 573.58 | 00 | 00 | 13165 | 9869 | 998 | 344.67 |  | 
2. | LS | 10500 | 763 | 90.68 | 281 | 35.13 | 00 | 00 | 4467 | 6033 | 500 | 71.09 |  | 
3. | PW | 3129 | 156 | 381.24 | 89 | 189.22 | 00 | 00 | 1565 | 1564 | 48 | 144.09 |  | 
4. | LAN | 920 | 14 | 7.2 | 6 | 3.08 | 00 | 00 | 639 | 281 |  |  |  | 
5. | PSS | 5862 | 15 | 13.28 | 8 | 7.32 | 00 | 00 | 4219 | 1643 |  |  |  | 
6. | TRENCH SLAB & Counter Weight |  |  |  |  |  | 56 | 94.80 |  |  |  |  |  | 
7. | RECAST ELEMENT |  |  |  |  |  | 8 | 0.36 |  |  |  |  |  | 
TOTAL |  |  | 2835 | 1250.38 | 1925 | 808.33 | 64 | 95.16 | 24055 | 19390 | 1546 | 559.85 | 1800 | 4107.35

## Slide 12
Sr No | Elements | Total Elements to be casted | Planned FTM February 24 | Concrete FTM February 24 | Achieved FTM February 24 | Concrete Consumed | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM February 24
1. | HCS |  | 00 BED | 00 | 22 BED | 334.46 |  | 22 BED | 00 |  | 2105.86
HCS Factory Person In charge – MR. RANA

## Slide 13
Sr No | Element/Description | Planned FTM February 24 | Achieved FTM February 24 | Plan For Next Month | Approved Cost/KGS | Cost/MTT FTM February 24 | Remarks
1. | STEEL FABRICATION | 00 | 17.50MTT | 00 | 00 | 28874.59 | 
FABRICATION Person In charge – MR. Ramdhyan Yadav

## Slide 14
BUILDING ERECTION WORK Person In charge – MR. ARUN SIR
Sr No | Element/Description | Planned FTM February 24 | Achieved FTM February 24 | Plan For Next Month | Remarks
1. | ERECTION BUILDING 18 | F10 TO F15 | F10 TO F12 | F13 TO F17 | 
2. | ERECTION BUILDING 19 | F4 TO F6 | F4 | F5 TO F7 | 
Flat finishing Work
Sr No | Total FlAT | Planned FTM February 24 | Achieved FTM February 24 | Plan For Next Month | Approved Cost/CMT | Cost/CMT FTM February 24
1. | 644 | 78 | 30 | 56 |  | 22447.94

## Slide 15: Special Mould & Other work Concrete Monthly Summary
Sr No | Grade | Unit | Theoretical Concrete (Element) | Cover Drain and other activities | Total Theoretical | Actual OLD RMC Concrete | Actual HCS RMC Concrete | Concrete Rejected | TOTAL OLD RMC & HCS RMC & POD RMC ACTUAL CONCRETE | Difference (Actual – Theoretical) | Difference %
1. | M10 | CUM | 00 | 24 | 24 | 24 |  | 00 | 24 | - | -
2. | M30 | CUM | 00 | 26.8 | 26.8 | 23.8 | 3 | 00 | 26.8 | - | -
3. | M40 | CUM |  | 14 | 14 | 14 |  | 00 | 14 | - | -
4. | M40 | CUM | 260.25 | 1.5 | 261.75 | 168.6 | 110.4 | 0 | 279 | 17.25 | 6.59
5. | M65 | CUM | 152.33 | 0 | 152.33 | 116.8 | 47.5 | 0 | 164.3 | 11.97 | 7.86
TOTAL |  | CUM | 412.58 | 66.3 | 478.88 | 347.2 | 160.9 | 00 | 508.1 | 29.22 | 6.10

## Slide 16
Pod Factory Concrete Monthly Summary
Sr No | Grade | Unit | Theoretical Concrete (Element) | Total Theoretical | Actual OLD RMC Concrete | Actual HCS RMC Concrete | POD BATCHING PLANT | Concrete Rejected | TOTAL OLD RMC & HCS RMC & POD RMC ACTUAL CONCRETE | Difference (Actual – Theoretical) | Difference %
1. | M65 | CUM | 1937.22 | 1937.2 | 173.1 | 154.6 | 1794.7 | 0 | 2122 | 185.2 | 9.56
TOTAL |  | CUM | 1937.22 | 1937.2 | 173.1 | 154.6 | 1794.7 | 0 | 2122 | 185.2 | 9.56

## Slide 17
Sr No | Grade | Unit | Theoretical Concrete (Element) | Other Work concrete | Total Theoretical Concrete | Reject Concrete | Total Actual Concrete | Difference (Actual – Theoretical) | Difference %
1. | M20 | CUM | 43.51 |  | 43.51 | 0 | 48.45 | 4.94 | 11.35
2. | M40 | CUM | 573.92 | 95.16 | 669.08 | 0 | 722.51 | 53.43 | 7.98
3. | M65 | CUM | 190.9 |  | 190.9 | 0 | 202.7 | 11.8 | 6.18
TOTAL |  | CUM | 808.33 |  | 903.49 | 0 | 973.66 | 70.17 | 7.77
Carousal Concrete Monthly Summary

## Slide 18
HCS Concrete Monthly Summary
Sr No | Grade | Unit | Theoretical Concrete (Element) | Reject Concrete | Actual Concrete | Total actual Concrete | Difference (Actual – Theoretical | Difference %
1. | M60 | CUM | 334.46 |  | 350.1 | 350.1 | 15.64 | 4.68
TOTAL |  | CUM |  |  |  | 350.1 | 15.64 | 4.68