## Slide 1: Production progress report FTM JANUARY 24.

## Slide 2: In House Labour Monthly Summary
Sr No | Month | Labour Cost | Concrete | Avg Cost/Cum
1. | April 22 | 2429680.2 | 543.72 | 4468.623942
2. | May 22 | 2471216.7 | 652.44 | 3787.653629
3. | June 22 | 2813211.5 | 662.05 | 4249.243305
4. | July 22 | 2655187.5 | 400.03 | 6637.47094
5. | August 22 | 2564097.2 | 445.05 | 5761.368783
6. | September 22 | 1990611.5 | 285.44 | 6973.834985
7. | October 22 | 2060881 | 386.6 | 5330.783756
8. | November 22 | 2662365 | 554.5425 | 4801.011645
9. | December 22 | 3995349.8 | 935.449 | 4268.789227
10. | January 23 | 4793114.919 | 971.5238 | 4933.605248
11. | February 23 | 5192192 | 2232.18 | 2326.0633
12. | March 23 | 4288932 | 903.2691 | 4748.232835
13. | April 23 | 5262161.03 | 824.24 | 6384.3
14. | May 23 | 5668339.00 | 1005.79 | 5635.70824
15. | June 23 | 7201632.00 | 1085.3411 | 6635.362836
16. | July 23 | 4682900.0 | 506.18 | 9251.45
17. | AUGUST 23 | 7961810.00 | 1315.51 | 6052.26

## Slide 3
Sr No | Month | Labour Cost | Concrete | Avg Cost/Cum
17. | AUGUST 23 | 7961810.00 | 1315.51 | 6052.26
18. | SEPTEMBER 23 | 10003410.00 | 1562.67 | 6401.48
19. | OCTOBER 23 | 10370522.4 | 1342.31 | 7725.89
20. | NOVEMBER 23 | 8979300.9 | 1195.89 | 7508.44
21. | DECEMBER 23 | 13128945.3 | 1862.61 | 7048.66
22. | JANUARY 24 | 18989157.59 | 3224.04 | 5889.87
In House Labour Monthly Summary

## Slide 4: Special Mould Area. Person in charge – MR. Arbab/IRFAN
Sr No | Elements | Total Elements to be casted | Planned FTM January 24 | Concrete FTM January 24 | Achieved FTM January 24 | Concrete Consumed | Unplanned Element | Unplanned Concrete | Produced Element | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM January 24
1. | PW | 3129 | 150 | 409.394 | 111 | 275.98 |  |  | 1397 | 1732 | 61 | 206.59 |  | 
2. | PSS | 5862 | 68 | 21.13 | 147 | 56.91 | 79 | 35.78 | 4098 | 1764 | 7 | 1.68 |  | 
3. | PB | 2806 | 369 | 162.08 | 295 | 147.14 |  |  | 2451 | 355 | 214 | 107.87 |  | 
4. | COUNTER WEIGHT |  |  |  |  |  | 1 | 0.7 |  |  |  |  |  | 
5. | LAN | 920 | 31 | 29.45 | 48 | 45.60 | 17 | 16.15 | 566 | 354 | 32 | 30.4 |  | 
TOTAL |  | 11889 | 618 | 622.054 | 601 | 525.63 | 97 | 52.63 | 8512 | 4205 | 314 | 346.54 | 1800 | 3721.81

## Slide 5: Pod Production Person in charge – MR. Rahil
Sr No | Elements | Total Elements to be casted | Plan FTM January 24 | Concrete FTM January 24 | Achieved FTM January 24 | Concrete Consumed | Unplanned Element | Unplanned Concrete | Produced Element | Balance to cast | Plan For Next Month | Concrete Consumption for next month | Approved Cost/CMT | Cost/CMT FTM January 24
1. | UT Kitchen POD - 1 | 217 | 21 | 159.6 | 29 | 219.24 | 8 | 59.64 | 209 | 8 | 44 | 334.4 |  | 
2. | UT Kitchen POD - 2 | 453 | 63 | 478.8 | 42 | 317.52 |  |  | 236 | 217 | 48 | 364.8 |  | 
3. | Lift POD | 92 | 8 | 39.76 | 12 | 53.77 | 4 | 14.01 | 47 | 45 | 15 | 74.55 |  | 
4. | LTKP - 1 | 60 | 12 | 91.2 | 13 | 98.28 | 1 | 7.56 | 60 | 0 |  |  |  | 
5. | LTKP - 2 | 60 |  |  |  |  |  |  | 60 | 0 |  |  |  | 
6. | LTKP – 3 | 30 | 6 | 45.6 | 5 | 37.8 |  |  | 30 | 0 |  |  |  | 
7. | LTKP - 4 | 30 |  |  |  |  |  |  | 30 | 0 |  |  |  | 
8. | RKP - 1 | 12 | 3 | 22.68 |  |  |  |  | 4 | 0 | 1 | 7.56 |  | 
9. | RKP - 2 | 8 | 8 | 60.8 |  |  |  |  |  |  |  |  |  | 
10. | MTKP - 1 | 12 | 20 | 152 |  |  |  |  |  |  |  |  |  | 
11. | MTKP - 2 | 12 | 6 | 45.6 | 11 | 83.16 | 5 | 37.56 | 14 | -2 |  |  |  | 

## Slide 6
Sr No | Elements | Total Elements to be casted | Plan FTM January 24 | Concrete FTM January 24 | Achieved FTM January 24 | Concrete Consumed | Unplanned Element | Unplanned Concrete | Produced Element | Balance to cast | Plan For Next Month | Concrete Consumption for next month | Approved Cost/CMT | Cost/CMT FTM January 24
12. | MTKP - 3 | 6 | 9 | 68.4 | 1 | 7.56 |  |  | 7 | 0 | 3 | 22.8 |  | 
13. | MTKP - 4 | 6 | 1 | 7.6 | 6 | 45.36 | 5 | 37.76 | 6 |  |  |  |  | 
14. | Kitchen POD – 101/102/103/104 | 140 | 119 | 1059.59 | 19 | 167.96 |  |  | 44 | 96 | 106 | 941.52 |  | 
15. | Lift POD 101/102/103/104 | 176 | 50 | 161.62 | 4 | 20.52 |  |  | 4 | 172 | 20 | 23.08 |  | 
15. | Kitchen pod FKP-01/02 | 72 |  |  |  |  |  |  | 36 | 36 |  |  |  | 
17. | Kitchen pod FKP-101/102 | 92 | 15 | 97.5 | 41 | 264.08 | 26 | 166.58 | 58 | 34 |  |  |  | 
TOTAL |  | 1478 | 341 | 2490.754 | 183 | 1315.25 | 49 | 323.11 | 845 | 606 | 237 | 1768.71 | 2200 | 4163.45

## Slide 7: Precast Factory STP Tank Work Person In charge – MR. Gauri.
Sr No | Description | UoM | Qty | Cost/CMT FTM January 23
1. | STP TANK WORK | CMT | 29 | 2373.75

## Slide 8: Element Repairing Person In charge – MR. Sivaraman.
Sr No | Element/Description | Planned FTM January 23 | Achieved FTM January 23 | Plan For Next Month | Approved Cost/CMT | Cost/CMT FTM January 23 | Remarks
1. | Element Handover | 00 | 241 | 00 | 500 | 1647.43 | 
Element Repairing Person In charge – MR. Amardeep
Sr No | Element/Description | Planned FTM January 23 | Achieved FTM January 23 | Plan For Next Month | Approved Cost/CMT | Cost/CMT FTM January 23 | Remarks
1. | Element Handover | 00 | 00 | 00 | 500 | 00 | 

## Slide 9: Reinforcement Yard Person In charge – MR. DK Patel.
Sr No | Element/Description | Planned FTM January 24 | Achieved FTM January 24 | Plan For Next Month | Approved Cost/KG | Cost/KG, MTT FTM January 24 | Remarks
1. | Reinforcement | 539.36 MTT | 317.89MTT | 329.78MTT | 15 | 11.11 | 
2. | AWM MACHINE |  | 40.32 MTT |  |  |  | 

## Slide 10
POD FINISHING Person In charge – MR. SIVARAMAN.
Sr No | Element/Description | Planned FTM January 24 | Achieved FTM January 24 | Plan For Next Month | Approved Cost/CUM | Cost/CUM FTM January 24 | Remarks
1. | Element Handover | 120 | 125 | 00 | 1050 | 2432.21 | 

## Slide 11
Carousal Factory Person In charge – MR. AMARDEEP
Sr No | Elements | Total Elements to be casted | Planned FTM January 24 | Concrete FTM January 24 | Achieved FTM January 24 | Concrete Consumed | Unplanned Element | Unplanned Element | Produced Element | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM January 24
1. | NLW | 23034 | 2166 | 939.36 | 1414 | 681.62 | 00 | 00 | 11624 | 11410 | 811 | 289.73 |  | 
2. | LS | 10500 | 288 | 40.49 | 180 | 23.46 | 00 | 00 | 4186 | 6314 | 223 | 32.88 |  | 
3. | PW | 3129 | 230 | 400.75 | 193 | 319.13 | 00 | 00 | 1397 | 1732 | 60 | 132.1 |  | 
4. | LAN | 920 | 16 | 8.2 | 24 | 12.28 | 00 | 00 | 566 | 354 |  |  |  | 
5. | PSS | 5862 | 28 | 15.36 | 35 | 24.94 | 00 | 00 | 4098 | 1764 |  |  |  | 
6. | TRENCH SLAB |  |  |  |  |  | 12 | 20.98 |  |  |  |  |  | 
7. | RECAST ELEMENT |  |  |  |  |  | 21 | 0.42 |  |  |  |  |  | 
TOTAL |  |  | 2728 | 1404.16 | 1846 | 1061.43 | 33 | 21.4 | 21871 | 21574 | 1094 | 454.71 | 1800 | 4313.51

## Slide 12
Sr No | Elements | Total Elements to be casted | Planned FTM January 24 | Concrete FTM January 24 | Achieved FTM January 24 | Concrete Consumed | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM January 24
1. | HCS |  | 11.1 BED | 197.80 | 22 BED | 299.63 |  | 0 BED | 00 |  | 1632.72
HCS Factory Person In charge – MR. RANA

## Slide 13
Sr No | Element/Description | Planned FTM January 24 | Achieved FTM January 24 | Plan For Next Month | Approved Cost/KGS | Cost/CMT FTM January 24 | Remarks
1. | STEEL FABRICATION | 00 | 18.56MTT | 00 | 00 | 17.67 | 
FABRICATION Person In charge – MR. Ramdhyan Yadav

## Slide 14
BUILDING ERECTION WORK Person In charge – MR. SATISH KUMAR
Sr No | Element/Description | Planned FTM January 24 | Achieved FTM January 24 | Plan For Next Month | Remarks
1. | ERECTION BUILDING 18 | F7 TO F10 | F7 TO F10 | F10 TO F15 | 
2. | ERECTION BUILDING 19 |  | F1 TO F3 | F4 TO F6 | 
Flat finishing Work
Sr No | Total FlAT | Planned FTM January 24 | Achieved FTM January 24 | Finishing bag Consumed | Plan For Next Month | Approved Cost/CMT | Cost/CMT FTM January 24
1. | 644 |  | 26 | 36 | 78 |  | 8791.50

## Slide 15: Special Mould & Pod Factory & Other work Concrete Monthly Summary
Sr No | Grade | Unit | Theoretical Concrete (Element) | Cover Drain and other activities | Total Theoretical | Actual OLD RMC Concrete | Actual HCS RMC Concrete | POD BATCHING PLANT | Concrete Rejected | TOTAL OLD RMC & HCS RMC & POD RMC ACTUAL CONCRETE | Difference (Actual – Theoretical) | Difference %
1. | M10 | CUM | 00 | 2 | 2 | 0 | 2 | - | 00 | 2 | - | -
2. | M40 | CUM | 00 | 27 | 27 | 0 | 27 | - | 00 | 27 | - | -
3. | M40 | CUM | 249.65 | 0.7 | 250.35 | 56.2 | 199.1 | - | 00 | 255.3 | 4.95 | 1.97
4. | M65 | CUM | 1591.23 | 00 | 1591.23 | 139.8 | 354.74 | 1210.05 | 1.8 | 1702.79 | 111.56 | 7.01
TOTAL |  | CUM | 1840.88 | 29.7 | 1870.58 | 196 | 582.84 | 1210.05 | 1.8 | 1987.09 | 116.51 | 6.22

## Slide 16
Sr No | Grade | Unit | Theoretical Concrete (Element) | Other Work concrete | Total Theoretical Concrete | Reject Concrete | Total Actual Concrete | Difference (Actual – Theoretical) | Difference %
1. | M20 | CUM | 504.10 |  | 504.10 | 00 | 554.05 | 49.95 | 9.91
2. | M40 | CUM | 238.20 | 21.40 | 259.6 | 00 | 271.91 | 12.31 | 4.74
3. | M65 | CUM | 319.13 |  | 319.13 | 00 | 328.55 | 9.42 | 2.95
TOTAL |  | CUM |  |  | 377.66 | 00 | 392.91 | 15.25 | 4.04
Carousal Concrete Monthly Summary

## Slide 17
HCS Concrete Monthly Summary
Sr No | Grade | Unit | Theoretical Concrete (Element) | Reject Concrete | Actual Concrete | Total actual Concrete | Difference (Actual – Theoretical | Difference %
1. | M60 | CUM | 299.63 |  | 319.6 | 319.6 | 19.97 | 6.66
TOTAL |  | CUM |  |  |  | 319.6 | 19.97 | 6.66