## Slide 1: Production Progress Report FTM JULY 24.

## Slide 2: In House Labour Rate Monthly Summary
To be continue…
Sr No | Month | Labour Cost (INR) | Concrete (Cum) | Labour (Nos) | Avg Cost/Cum
1. | Apr-22 | 24,29,680 | 544 | 120 | 4469
2. | May-22 | 24,71,217 | 652 | 122 | 3788
3. | Jun-22 | 28,13,212 | 662 | 127 | 4249
4. | Jul-22 | 26,55,188 | 400 | 125 | 6637
5. | Aug-22 | 25,64,097 | 445 | 116 | 5761
6. | Sep-22 | 19,90,612 | 285 | 111 | 6974
7. | Oct-22 | 20,60,881 | 387 | 102 | 5331
8. | Nov-22 | 26,62,365 | 555 | 145 | 4801
9. | Dec-22 | 39,95,350 | 935 | 195 | 4269
10. | Jan-23 | 47,93,115 | 972 | 233 | 4934
11. | Feb-23 | 51,92,192 | 2232 | 249 | 2326
12. | Mar-23 | 42,88,932 | 903 | 253 | 4748
13. | Apr-23 | 52,62,161 | 824 | 209 | 6384
14. | May-23 | 56,68,339 | 1006 | 277 | 5636
15. | Jun-23 | 72,01,632 | 1085 | 343 | 6635
16. | Jul-23 | 46,82,900 | 506 | 193 | 9251
17. | Aug-23 | 79,61,810 | 1316 | 370 | 6052

## Slide 3
In House Labour Rate Monthly Summary
Sr No | Month | Labour Cost (INR) | Concrete (Cum) | Labour (Nos) | Avg Cost/Cum
18. | Sep-23 | 10,003,410 | 1563 | 442 | 6401
19. | Oct-23 | 10,370,522 | 1342 | 454 | 7726
20. | Nov-23 | 8,979,301 | 1196 | 429 | 7508
21. | Dec-23 | 13,128,945 | 1863 | 584 | 7049
22. | Jan-24 | 18,989,158 | 3224 | 877 | 5890
23. | Feb-24 | 21,732,402 | 3589 | 949 | 6055
24. | Mar-24 | 22,651,394 | 3731 | 1009 | 6072
25. | Apr-24 | 20,895,183 | 3008 | 915 | 6947
26. | May-24 | 22,060,451 | 3467 | 997 | 6363
27. | Jun-24 | 24000480 | 3524 | 1050 | 6811
28. | July-24 | 18947767 | 2404 | 989 | 7882

## Slide 4
Chart: Concrete & Labour
| Apr-22 | May-22 | Jun-22 | Jul-22 | Aug-22 | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Concrete (Cum) | 544 | 652 | 662 | 400 | 445 | 285 | 387 | 555 | 935 | 972 | 2232 | 903 | 824 | 1006 | 1085 | 506 | 1316 | 1563 | 1342 | 1196 | 1863 | 3224 | 3589 | 3731 | 3008 | 3467 | 3524 | 2404
Labour (Nos) | 120 | 122 | 127 | 125 | 116 | 111 | 102 | 145 | 195 | 233 | 249 | 253 | 209 | 277 | 343 | 193 | 370 | 442 | 454 | 429 | 584 | 877 | 949 | 1009 | 915 | 997 | 1050 | 989
Chart: Avg Cost/Cum
| Apr-22 | May-22 | Jun-22 | Jul-22 | Aug-22 | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Avg Cost/Cum | 4469 | 3788 | 4249 | 6637 | 5761 | 6974 | 5331 | 4801 | 4269 | 4934 | 2326 | 4748 | 6384 | 5636 | 6635 | 9251 | 6052 | 6401 | 7726 | 7508 | 7049 | 5890 | 6055 | 6072 | 6947 | 6363 | 6811 | 7882

## Slide 5: Special Mould Area: Person in charge – MR. VITRANG
 |  | PLAN FTM JULY 24 |  | ACHIEVED FTM JULY 24 |  |  |  | PLAN FTM AUGUST 24 | 
Sr No | Elements | NOS | CUM | NOS | CUM | EXTRA NOS | EXTRA CUM | NOS | CUM
1. | PW | 68 | 217 | 56 | 158 |  |  | 68 | 231
2. | PSS | 101 | 29 | 36 | 13 |  |  | 90 | 39
3. | PB | 145 | 64 | 151 | 70 |  |  | 64 | 27
4. | PPW |  |  |  |  |  |  |  | 
5. | LAN | 10 | 10 | 10 | 10 |  |  | 5 | 5
TOTAL |  | 324 | 320 | 253 | 250 | 0 | 0 | 227 | 302
 | % |  |  | 78% | 78% |  |  |  | 
Chart: Special Mould Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413 | 45444 | 45474
Actual Cost (Rs/cum) | 6630.6668 | 7332.5702 | 4398.3207 | 3721.8117 | 4881.4204 | 5909.2193 | 5914.6348 | 3484.5371 | 3215.2245 | 3259.8643
Approved Cost (Rs/cum) | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800

## Slide 6
Element Repairing Person In charge – MR. VITRANG
 |  | PLAN FTM MAY 24 | ACHIEVED FTM MAY 24 | PLAN FTM JUNE 24
Sr No | Element | NOS | NOS | NOS
1. | NLW |  |  | 
2. | PSS |  | 157 | 
3. | PW |  |  | 
4. | PB |  | 268 | 
5. | LAN |  | 34 | 
TOTAL |  |  | 459 | 
Chart: Special Mould Factory Element Repair Cost Performance
| 45413
Actual Cost (Rs/cum) | 758.4376
Approved Cost (Rs/cum) | 500

## Slide 7
Carousal Factory: Person In charge – MR. VITRANG
 |  | PLAN FTM JULY 24 |  | ACHIEVED FTM JULY 24 |  |  |  | PLAN FTM AUGUST 24 | 
Sr | Elements | NOS | CUM | NOS | CUM | EXTRA NOS | EXTRA CUM | NOS | CUM
1. | NLW | 864 | 359 | 455 | 139 |  |  | 844 | 379
2. | LS | 375 | 48 | 1143 | 129 |  |  | 120 | 18
3. | PW | 110 | 220 | 80 | 124 |  |  | 184 | 413
4. | LAN | 15 | 9 | 16 | 9 |  |  | 31 | 18
5. | PSS | 14 | 11 | 87 | 90 |  |  | 14 | 13
6. | PPW | 1 | 0.42 |  |  |  |  | 1 | 0
7. | Road Barrier |  |  |  |  | 2 | 1.4 |  | 
TOTAL |  | 1379 | 648 | 1781 | 489 | 2 | 1.4 | 1194 | 842
 | % |  |  | 94% | 74% |  |  |  | 
Chart: Carousal Factory Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413 | 45444 | 45474
Actual Cost (Rs/cum) | 5630.5074 | 3256.9825 | 6918.8038 | 4313.5078 | 4107.3463 | 5262 | 7417.9145 | 5497.0232 | 4361.5259 | 5212.8907
Approved Cost (Rs/cum) | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800

## Slide 8
Element Repairing Person In charge – MR. VITRANG
 |  | PLAN FTM MAY 24 | ACHIEVED FTM MAY 24 | PLAN FTM JUNE 24
Sr No | Element | NOS | NOS | NOS
1. | NLW |  | 71 | 
2. | PSS |  | 2 | 
3. | PW |  | 10 | 
4. | PB |  |  | 
5. | LS |  | 76 | 
TOTAL |  |  | 159 | 
Chart: Carousal Factory Element Repair Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413
Actual Cost (Rs/cum) | 961.8276 | 976.8835 | 1146.4761 | 0 | 1571.1058 | 664.7746 | 1276.5157 | 1466.9766
Approved Cost (Rs/cum) | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500

## Slide 9: Pod Production: Person in charge – MR. Rahil
 |  | PLAN FTM JULY 24 |  | ACHIEVED FTM JULY 24 |  |  |  | PLAN FTM AUGUST 24 | 
Sr No | Elements | NOS | CUM | NOS | CUM | EXTRA NOS | EXTRA CUM | NOS | CUM
1. | Kitchen POD | 362 | 3035 | 144 | 1199 |  |  | 175 | 1548
2. | Lift POD | 26 | 133 | 25 | 105 |  |  | 39 | 280
3. | Road Barrier |  |  |  |  | 9 | 6.3 |  | 
TOTAL |  | 388 | 3168 | 169 | 1305 | 9 | 6.3 | 214 | 1828
 | % |  |  | 44% | 41% |  |  |  | 
Chart: Pod Factory Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413 | 45444 | 45474
Actual Cost (Rs/cum) | 4449.8318 | 3793.9381 | 3754.0823 | 4163.4473 | 4295.0106 | 3691 | 3766.9354 | 3430.1889 | 4226.7129 | 5375.0956
Approved Cost (Rs/cum) | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200

## Slide 10
 |  | PLAN FTM JULY 24 |  | ACHIEVED FTM JULY 24 |  | PLAN FTM AUGUST 24 | 
Sr No | Elements | NOS | CUM | NOS | CUM | NOS | CUM
1. | HCS | 45BED | 720 | 27BED | 352 | 46BED | 743
 | TOTAL | 45BED | 720 | 27BED | 352 | 46BED | 743
HCS Factory: Person In charge – MR. RANA
NOTE - PLAN TO BE REVISED AS PER ERECTION REQUIREMENT.
Chart: HCS Factory Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413 | 45444 | 45474
Actual Cost (Rs/cum) | 3485.2451 | 2596.5348 | 3262.035 | 1632.7197 | 2105.8577 | 2183 | 2318.253 | 2653.1206 | 1990.5807 | 1764.353
Approved Cost (Rs/cum) | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200

## Slide 11: Reinforcement Yard: Person In charge – MR. DK Patel.
 |  | PLAN FTM JULY 24 | ACHIEVED FTM JULY 24 | PLAN FTM AUGUST 24
Sr No | Element | MTT | MTT | MTT
1. | REINFORCEMENT | 545 | 261 | 363
TOTAL |  | 545 | 261 | 363
 | % |  | 48% | 
Chart: Reinforcement Factory Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413 | 45444 | 45474
Actual Cost (Rs/KGS) | 13.9378 | 16.3846 | 11.1359 | 11.1096 | 11.4875 | 8.8383 | 11.8362 | 9.1871 | 11.5384 | 11.8501
Approved Cost (Rs/KGS) | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## Slide 12: CIVIL Work Person In charge – MR. Gauri.
Sr No | Description | UoM | Qty | Cost/CMT FTM MAY 24
1. | CIVIL WORK | CMT | 7 | 25502

## Slide 13: 2D Element Repairing: Person In charge – MR. Sivaraman.
 |  | PLAN FTM JULY 24 | ACHIEVED FTM JULY 24 | PLAN FTM AUGUST 24
Sr No | Element | NOS | NOS | NOS
1. | NLW |  |  | 
2. | PB |  | 4 | 
3. | PSS |  | 51 | 
4. | PPW |  | 28 | 
5. | LAN |  |  | 
TOTAL |  | 00 | 83 | 00
Chart: Hospital Area Element Repair Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413 | 45444 | 45474
Actual Cost (Rs/cum) | 342.5595 | 548.3994 | 972.0185 | 1647.4268 | 1295.5018 | 1406.1903 | 1426 | 755.2916 | 626.1033 | 583.4009
Approved Cost (Rs/cum) | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500

## Slide 14
POD ERECTION: Person In charge – MR. SIVARAMAN.
 |  | PLAN FTM JULY 24 | ACHIEVED FTM JULY 24 | PLAN FTM AUGUST 24
Sr No | Element | NOS | NOS | NOS
1. | POD |  | 186 | 
TOTAL |  |  | 186 | 
Chart: Pod Erection Cost Performance
| 45323 | 45352 | 45383 | 45413 | 45444 | 45474
Actual Cost (Rs/Pod) | 8283.9067 | 6419 | 9138.4767 | 6996.7973 | 7402.7824 | 7754.3161
Approved Cost (Rs/Pod) | 4000 | 4000 | 4000 | 4000 | 4000 | 4000

## Slide 15
POD FINISHING(FACTORY): Person In charge – MR. SIVARAMAN.
 |  | PLAN FTM JULY 24 | ACHIEVED FTM JULY 24 | PLAN FTM AUGUST 24
Sr No | Element | NOS | NOS | NOS
1. | POD | 200 | 260 | 300
TOTAL |  |  | 260 | 
 | % |  | 130% | 
Chart: Pod Finishing Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413 | 45444 | 45474
Actual Cost (Rs/cum) | 2239.73 | 1683.5431 | 2158.2336 | 2432.2128 | 2067.3323 | 2168.5961 | 1855.1424 | 1291.7321 | 1407.1706 | 1304.0332
Approved Cost (Rs/cum) | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050

## Slide 16
POD FINISHING(HOSPITAL AREA): Person In charge – MR. SIVARAMAN.
 |  | PLAN FTM JULY 24 | ACHIEVED FTM JULY 24 | PLAN FTM AUGUST 24
Sr No | Element | NOS | NOS | NOS
1. | POD | 100 | 73 | 200
TOTAL |  |  | 73 | 
 | % |  | 73% | 
Chart: Pod Finishing Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413 | 45444 | 45474
Actual Cost (Rs/cum) | 1855.2831 | 1437.2985
Approved Cost (Rs/cum) | 1050 | 1050

## Slide 17
FABRICATION: Person In charge – MR. Ramdhyan Yadav
 |  | PLAN FTM JULY 24 | ACHIEVED FTM JULY 24 | PLAN FTM AUGUST 24
Sr No | Element | KGS | KGS | KGS
1. | POD(A3 & A4,LPM2) MODIFICATION, POD DOOR WINDOW FABRICATION WORK |  | 46000 | 
TOTAL |  |  | 46000 | 
 | % |  |  | 
Chart: Fabrication Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413 | 45444 | 45474
Approved Cost (Rs/KGS)
Actual Cost (Rs/KGS) | 14.3433 | 36.5722 | 20.421 | 17.6667 | 28.8746 | 9.2937 | 15 | 14.4495 | 12.1972 | 16.3724

## Slide 18
BUILDING ERECTION WORK: Person In charge – MR. ARUN SIR
CYCLE TIME BUILDING 18 |  | PLAN FTM MAR 24 |  |  |  |  |  |  |  |  |  |  |  |  |  | ACHIEVED FTM APRIL 24 |  |  |  |  |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9 | F10 | F11 | F12 | F13 | F14 | F15 | F16 | F17 | F18 | F19 | F20 | F21 | F22
1. | T1 | 41 | 11 | 20 | 18 | 15 | 8 | 9 | 10 | 11 | 7 | 19 | 9 | 7 | 9 | 14 | 17 | 19 | 14 | 15 | 11 | 17 | 14
2. | T2 | 47 | 12 | 24 | 14 | 10 | 7 | 13 | 9 | 10 | 6 | 5 | 7 | 10 | 8 | 17 | 15 | 19 | 21 | 14 | 12 | 16 | 13
Chart: 
| Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | 2023 | 2024
POD | 32 | 47 | 54 | 96 | 110 | 96 | 87 | 53 | 66 | 71 | 20

## Slide 19
CYCLE TIME BUILDING 19 |  | PLAN FTM MAR 24 |  |  |  |  |  |  |  |  |  |  |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9 | F10 | F11 | F12 | F13 | F14
1. | TYPE3 | 37 | 18 | 16 | 16 | 12 | 9 | 21 | 12 | 24 | 16 | 17 | 18 | 10 | 17
2. | TYPE4 | 40 | 21 | 14 | 16 | 23 | 55 | 19 | 42 |  |  |  |  |  | 
3. | TYPE5 | 44 | 22 | 11 | 15 | 23 | 63 | 53 |  |  |  |  |  |  | 
Chart: 
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | 2023 | 2024
POD | 6 | 62 | 53 | 83 | 68 | 52 | 43 | 49 | 34

## Slide 20
CYCLE TIME BUILDING 14 |  | PLAN FTM MAR 24 |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4
1. | TYPE1 | 107 | 44 | 22 | 
2. | TYPE2 | 116 | 39 |  | 
CYCLE TIME BUILDING 16 |  | PLAN FTM MAR 24 |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4
1. | TYPE1 | 116 | 22 |  | 
2. | TYPE2 | 122 | 25 |  | 
CYCLE TIME BUILDING 15 |  | PLAN FTM MAR 24 |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4
1. | TYPE3 | 115 | 33 |  | 
2. | TYPE4 | 108 | 34 | 20 | 
3. | TYPE5 | 125 | 27 |  | 
87/27 = 3.22 POD Per Day
Chart: POD ERECTION PER MONTH
| Feb | Mar | Apr | May | Jun | Jul
POD | 25 | 4 | 19 | 15 | 27 | 18
Chart: POD ERECTION PER MONTH
| Feb | Mar | Apr | May | Jun | Jul
POD | 24 | 10 | 3 | 31 | 24 | 37
Chart: POD ERECTION PER MONTH
| Mar | Apr | May | Jun | Jul
POD | 27 | 5 | 18 | 9 | 32

## Slide 21
CYCLE TIME BUILDING 17 |  | PLAN FTM MAR 24 |  |  |  |  |  |  |  |  |  |  |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9 | F10 | F11 | F12 | F13 | F14
1. | TYPE9 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2. | TYPE10 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3. | TYPE11 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4. | TYPE12 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Chart: POD ERECTION PER MONTH
| Jul | 2024 | POD
Total | 40
40/27 = 1.48 POD Per Day

## Slide 22
BUILDING FLAT FINISHING WORK: Person In charge – MR. ARUN SIR
 |  | PLAN FTM JULY 24 | ACHIEVED FTM JULY 24 | PLAN FTM AUGUST 24
Sr No | Element | NOS | NOS | NOS
1. | FLAT | 120 | 149 | 00
TOTAL |  | 120 | 149 | 00
 | % |  | 124% | 
8131/16.5 = 493 INR Per cum
Chart: Flat Finishing Cost Performance
| 45292 | 45323 | 45352 | 45383 | 45413 | 45444 | 45474
Actual Cost (Rs/FLAT) | 8791.5 | 22447.938 | 10338 | 8651.2065 | 11843.15 | 9980.7542 | 8175.3884
Approved Cost (Rs/FLAT)

## Slide 23
BATCHING PLANT: Person In charge – MR. PRABHU UPADHYAY
 |  | PLAN FTM JULY 24 | ACHIEVED FTM JULY 24 |  | PLAN FTM AUGUST 24
Sr No | Batching Plant | CUM | CUM | EXTRA CUM | CUM
1. | COMMON | 2212 | 761 |  | 1933
2. | HCS | 1058 | 808 |  | 998
3. | CAROUSAL | 1254 | 506 |  | 774
4. | POD | 2231 | 1149 |  | 1378
TOTAL |  | 6755 | 3224 |  | 5083
 | % |  | 48% |  | 
Chart: All Batching Plant
| 45474
Approved Cost (Rs/CUM)
Actual Cost (Rs/CUM) COMMON | 60.52
Actual Cost (Rs/CUM) HCS | 93.8235
Actual Cost (Rs/CUM) CAROUSAL | 181.3053
Actual Cost (Rs/CUM) POD | 116.3552

## Slide 24
MAINTENANCE Person In charge – MR. AHUJA SIR
BUDGET 2023-2024 |  | BUDGET |  | 
Sr No | DISCRIPTION | BUDGET | EXPENSES | BALANCE
1. |  |  |  | 
BREAKDOWN REPORT |  | BUDGET | 
Sr No | NAME | NOS OF DAY | NOS OF HOURS
1. |  |  | 
STAFF HIRING 2023-2024 |  | BUDGET | 
Sr No | DESIGNATION | AVAILABLE | REQUIRED
1. |  |  | 

## Slide 25
FUEL EFFICIENCY OF MACHINE |  | BUDGET
Sr No | MACHINE NAME | MACHINE EFFICIENCY
1. |  | 

## Slide 26
CONCRETE SUMMARY
FACTORY WISE

## Slide 27: Concrete Monthly Summary: Special Mould
 |  |  | THEORETICAL CONCRETE |  |  | ACTUAL CONCRETE |  |  |  |  | DIFFERENCE | 
Sr | Grade | Unit | ELEMENT | Other Work | Total | COMMON RMC | HCS RMC | CUBE | Rejected | Total | Difference | %
1 | M40 | CUM | 91 |  | 91 | 54 | 42 | 1 | 0 | 95 | 4 | 4%
2 | M65 | CUM | 159 |  | 159 | 124 | 51 | 1 | 0 | 174 | 15 | 10%
TOTAL |  | CUM | 250 |  | 250 | 178 | 93 | 2 | 0 | 269 | 19 | 8%

## Slide 28
Concrete Monthly Summary: Pod Factory
 |  |  | THEORETICAL CONCRETE |  |  | ACTUAL CONCRETE |  |  |  |  |  | DIFFERENCE | 
Sr No | Grade | Unit | Element | Road Barrier | Total | Common RMC | HCS RMC | POD RMC | CUBE & CLEANING | Rejected | TOTAL | Difference | %
1 | M65 | CUM | 1305 | 6 | 1311 | 106 | 76 | 1149 | 18 | 3 | 1310 | -1 | -0.09%
TOTAL |  | CUM | 1305 | 6 | 1311 | 106 | 76 | 1149 | 18 | 3 | 1310 | -1 | -0.09%

## Slide 29
 |  |  | THEORETICAL CONCRETE |  |  | ACTUAL CONCRETE |  |  |  | DIFFERENCE | 
Sr | Grade | Unit | ELEMENT | Road Barrier | Total | Actual | CUBE & CLEANING | Reject | Total | Difference | %
1 | M20 | CUM | 19 | 0.35 | 19 | 22 | 0.26 | 0 | 22 | 3 | 13%
2 | M40 | CUM | 225 | 0.35 | 225 | 233 | 1.30 | 1 | 230 | 5 | 2%
3 | M25 | CUM | 120 |  | 120 | 118 | 0.92 | 0 | 118 | -3 | -2%
4 | M65 | CUM | 126 | 0.70 | 127 | 133 | 0.99 | 0 | 132 | 5 | 4%
TOTAL |  | CUM | 490 | 1.40 | 491 | 506 | 3.47 | 1 | 501 | 10 | 2%
July 24 Concrete Monthly Summary: Carousal

## Slide 30
JULY 24 Concrete Monthly Summary: HCS
 |  |  | THEORETICAL CONCRETE | THEORETICAL CONCRETE | ACTUAL CONCRETE |  |  |  | DIFFERENCE | 
Sr No | Grade | Unit | Element | Total | Actual | CUBE | Rejected | Total | Difference | %
1 | M60 | CUM | 352 | 352 | 391 | 1.16 | 1 | 388 | 36 | 10%
TOTAL |  | CUM | 352 | 352 | 391 | 1.16 | 1 | 388 | 36 | 10%

## Slide 31
THANK YOU