## Slide 1: Production progress report FTM MARCH 24.

## Slide 2: In House Labour Monthly Summary
Sr No | Month | Labour Cost | Concrete | Avg Cost/Cum
1. | April 22 | 2429680 | 544 | 4469
2. | May 22 | 2471217 | 652 | 3788
3. | June 22 | 2813212 | 662 | 4249
4. | July 22 | 2655188 | 400 | 6637
5. | August 22 | 2564097 | 445 | 5761
6. | September 22 | 1990612 | 285 | 6974
7. | October 22 | 2060881 | 387 | 5331
8. | November 22 | 2662365 | 555 | 4801
9. | December 22 | 3995350 | 935 | 4269
10. | January 23 | 4793115 | 972 | 4934
11. | February 23 | 5192192 | 2232 | 2326
12. | March 23 | 4288932 | 903 | 4748
13. | April 23 | 5262161 | 824 | 6384
14. | May 23 | 5668339 | 1006 | 5636
15. | June 23 | 7201632 | 1085 | 6635
16. | July 23 | 4682900 | 506 | 9251
17. | AUGUST 23 | 7961810 | 1316 | 6052

## Slide 3
Sr No | Month | Labour Cost | Concrete | Avg Cost/Cum
17. | AUGUST 23 | 7961810 | 1316 | 6052
18. | SEPTEMBER 23 | 10003410 | 1563 | 6401
19. | OCTOBER 23 | 10370522 | 1342 | 7726
20. | NOVEMBER 23 | 8979301 | 1196 | 7508
21. | DECEMBER 23 | 13128945 | 1863 | 7049
22. | JANUARY 24 | 18989158 | 3224 | 5890
23. | February 24 | 21732402 | 3589 | 6055
24. | March 24 | 22651394 | 3731 | 6072
In House Labour Monthly Summary

## Slide 4: Special Mould Area. Person in charge – MR. VITRANG
 |  | PLAN FTM MAR 24 |  | ACHIEVED FTM MAR 24 |  |  |  | PLAN FTM UPTO 19 APRIL 24 | 
Sr No | Elements | NOS | CUM | NOS | CUM | EXTRA NOS | EXTRA CUM | NOS | CUM
1. | PW | 86 | 320 | 10 | 38 |  |  | 73 | 106
2. | PSS | 30 | 6 | 31 | 7 | 1 | 1 | 9 | 3
3. | PB | 394 | 176 | 416 | 186 | 22 | 10 | 81 | 74
4. | MANHOLE |  |  |  |  | 24 | 6 |  | 
5. | LAN | 46 | 44 | 46 | 44 |  |  | 8 | 21
TOTAL |  | 556 | 546 | 503 | 275 | 47 | 17 | 171 | 204
 | % |  |  | 90% | 50% |  |  |  | 
Chart: Special Mould Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual Cost (Rs/cum) | 6630.6668 | 7332.5702 | 4398.3207 | 3721.8117 | 4881.4204 | 5909.2193
Approved Cost (Rs/cum) | 1800 | 1800 | 1800 | 1800 | 1800 | 1800

## Slide 5
Carousal Factory Person In charge – MR. VITRANG
 |  | PLAN FTM MAR 24 |  | ACHIEVED FTM MAR 24 |  |  |  | PLAN FTM UPTO 19 APRIL 24 | 
Sr | Elements | NOS | CUM | NOS | CUM | EXTRA NOS | EXTRA CUM | NOS | CUM
1. | NLW | 1716 | 603 | 1148 | 417 |  |  | 683 | 268
2. | LS | 548 | 75 | 268 | 31 |  |  | 598 | 81
3. | PW | 82 | 203 | 21 | 56 |  |  | 91 | 209
4. | LAN | 14 | 7 | 8 | 4 |  |  | 13 | 6
5. | PSS | 5 | 5 | 2 | 3 |  |  | 25 | 27
6. | Counter Weight |  |  |  |  | 43 | 78 |  | 
TOTAL |  | 2365 | 894 | 1447 | 511 | 43 | 78 | 1410 | 592
 | % |  |  | 61% | 57% |  |  |  | 
Chart: Carousal Factory Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual Cost (Rs/cum) | 5630.5074 | 3256.9825 | 6918.8038 | 4313.5078 | 4107.3463 | 5561.9105
Approved Cost (Rs/cum) | 1800 | 1800 | 1800 | 1800 | 1800 | 1800

## Slide 6
Element Repairing Person In charge – MR. VITRANG
 |  | PLAN FTM MAR 24 | ACHIEVED FTM Mar 24 | PLAN FTM APRIL 24
Sr No | Element | NOS | NOS | NOS
1. | NLW |  | 199 | 
2. | LS |  | 43 | 
3. | PW |  | 84 | 
TOTAL |  |  | 326 | 
Chart: Carousal Factory Element Repair Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual Cost (Rs/cum) | 961.8276 | 976.8835 | 1146.4761 | 0 | 1571.1058 | 664.7746
Approved Cost (Rs/cum) | 500 | 500 | 500 | 500 | 500 | 500

## Slide 7: Pod Production Person in charge – MR. Rahil
 |  | PLAN FTM MAR 24 |  | ACHIEVED FTM MAR 24 |  |  |  | PLAN FTM UPTO 19 APRIL 24 | 
Sr No | Elements | NOS | CUM | NOS | CUM | EXTRA NOS | EXTRA CUM | NOS | CUM
1. | Kitchen POD | 441 | 3752 | 285 | 2294 |  |  | 202 | 1738
2. | Lift POD | 23 | 107 | 51 | 272 | 28 | 165 | 20 | 45
TOTAL |  | 464 | 3859 | 336 | 2566 | 28 | 165 | 222 | 1783
 | % |  |  | 72% | 66% |  |  |  | 
Chart: Pod Factory Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual Cost (Rs/cum) | 4449.8318 | 3793.9381 | 3754.0823 | 4163.4473 | 4295.0106 | 3691.1266
Approved Cost (Rs/cum) | 2200 | 2200 | 2200 | 2200 | 2200 | 2200

## Slide 8
 |  | PLAN FTM MAR 24 |  | ACHIEVED FTM MAR 24 |  | PLAN FTM UPTO 19 APRIL 24 | 
Sr No | Elements | NOS | CUM | NOS | CUM | NOS | CUM
1. | HCS | 27 BED | 00 | 20 BED | 294 | 0 BED | 00
HCS Factory Person In charge – MR. RANA
Chart: HCS Factory Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual Cost (Rs/cum) | 3485.2451 | 2596.5348 | 3262.035 | 1632.7197 | 2105.8577 | 2182.8669
Approved Cost (Rs/cum) | 1200 | 1200 | 1200 | 1200 | 1200 | 1200

## Slide 9: CIVIL Work Person In charge – MR. Gauri.
Sr No | Description | UoM | Qty | Cost/CMT FTM March 24
1. | CIVIL WORK | CMT | 87.3 | 2648

## Slide 10: Element Repairing Person In charge – MR. Sivaraman.
 |  | PLAN FTM MAR 24 | ACHIEVED FTM Mar 24 | PLAN FTM APRIL 24
Sr No | Element | NOS | NOS | NOS
1. | NLW |  | 48 | 150
2. | PB |  | 291 | 400
3. | PSS |  | 435 | 400
4. | PW |  | 52 | 100
TOTAL |  |  | 826 | 1050
Chart: Hospital Area Element Repair Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual Cost (Rs/cum) | 342.5595 | 548.3994 | 972.0185 | 1647.4268 | 1295.5018 | 1406.1903
Approved Cost (Rs/cum) | 500 | 500 | 500 | 500 | 500 | 500

## Slide 11: Reinforcement Yard Person In charge – MR. DK Patel.
 |  | PLAN FTM MAR 24 | ACHIEVED FTM Mar 24 | PLAN FTM UPTO 19 APRIL 24
Sr No | Element | KGS | KGS | KGS
1. | REINFORCEMENT | 624 | 298 | 337
2. | AWM |  | 199 | 
TOTAL |  |  |  | 
 | % |  | 80% | 
Chart: Reinforcement Factory Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual Cost (Rs/KGS) | 13.9378 | 16.3846 | 11.1359 | 11.1096 | 11.4875 | 9.2837
Approved Cost (Rs/KGS) | 12 | 12 | 12 | 12 | 12 | 12

## Slide 12
POD FINISHING Person In charge – MR. SIVARAMAN.
 |  | PLAN FTM MAR 24 | ACHIEVED FTM Mar 24 | PLAN FTM APRIL 24
Sr No | Element | NOS | NOS | NOS
1. | POD | 00 | 24 | 100
TOTAL |  |  | 24 | 100
 | % |  |  | 
Chart: Pod Finishing Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Actual Cost (Rs/cum) | 2239.73 | 1683.5431 | 2158.2336 | 2432.2128 | 2067.3323 | 2168.5961
Approved Cost (Rs/cum) | 1050 | 1050 | 1050 | 1050 | 1050 | 1050

## Slide 13
POD ERECTION Person In charge – MR. SIVARAMAN.
 |  | PLAN FTM MAR 24 | ACHIEVED FTM Mar 24 | PLAN FTM APRIL 24
Sr No | Element | NOS | NOS | NOS
1. | POD |  | 277 | 
TOTAL |  |  | 277 | 
 | % |  |  | 
Chart: Pod Erection Cost Performance
| 45323 | 45352
Actual Cost (Rs/Pod) | 8283.9067 | 6419.4139
Approved Cost (Rs/Pod) | 4000 | 4000

## Slide 14
FABRICATION Person In charge – MR. Ramdhyan Yadav
 |  | PLAN FTM MAR 24 | ACHIEVED FTM Mar 24 | PLAN FTM APRIL 24
Sr No | Element | KGS | KGS | KGS
1. | POD MODIFICATION FABRICATION WORK |  | 75711 | 
TOTAL |  |  | 75711 | 
 | % |  |  | 
Chart: Fabrication Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352
Approved Cost (Rs/KGS)
Actual Cost (Rs/KGS) | 14.3433 | 36.5722 | 20.421 | 17.6667 | 28.8746 | 9.3229

## Slide 15
BUILDING ERECTION WORK Person In charge – MR. ARUN SIR
CYCLE TIME BUILDING 18 |  | PLAN FTM MAR 24 |  |  |  |  |  |  |  |  |  |  |  |  |  | ACHIEVED FTM APRIL 24
Sr | FLOOR | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9 | F10 | F11 | F12 | F13 | F14 | F15
1. | TYPE1 |  | 11 | 20 | 18 | 15 | 8 | 9 | 10 | 11 | 7 | 19 | 9 | 7 | 9 | 14
2. | TYPE2 |  | 12 | 24 | 14 | 10 | 7 | 13 | 9 | 10 | 6 | 5 | 7 | 10 | 8 | 17
Chart: 
| POD
2023 - Sep | 28
2023 - Oct | 43
2023 - Nov | 47
2023 - Dec | 83
2024 - Jan | 98
2024 - Feb | 86
2024 - Mar | 77

## Slide 16
CYCLE TIME BUILDING 19 |  | PLAN FTM MAR 24 |  |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4 | F5
1. | TYPE1 |  | 21 | 14 | 16 | 23
2. | TYPE2 |  | 22 | 11 | 15 | 23
Chart: 
| Nov | Dec | Jan | Feb | Mar | 2023 | 2024
POD | 6 | 58 | 47 | 75 | 55

## Slide 17
CYCLE TIME BUILDING 14 |  | PLAN FTM MAR 24 |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4
1. | TYPE1 |  |  |  | 
2. | TYPE2 |  |  |  | 
CYCLE TIME BUILDING 16 |  | PLAN FTM MAR 24 |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4
1. | TYPE1 |  |  |  | 
2. | TYPE2 |  |  |  | 
CYCLE TIME BUILDING 15 |  | PLAN FTM MAR 24 |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4
1. | TYPE1 |  |  |  | 
2. | TYPE2 |  |  |  | 
Chart: 
| Feb | Mar | 2024
POD | 26 | 4
Chart: 
| Mar | 2024
POD | 27
Chart: 
| Feb | Mar | 2024
POD | 24 | 10

## Slide 18
BUILDING FLAT FINISHING WORK Person In charge – MR. ARUN SIR
 |  | PLAN FTM MAR 24 | ACHIEVED FTM Mar 24 | PLAN FTM APRIL 24
Sr No | Element | NOS | NOS | NOS
1. | FLAT | 56 | 66 | 112
TOTAL |  | 56 | 66 | 112
 | % |  | 117% | 
Chart: Flat Finishing Cost Performance
| 45292 | 45323 | 45352
Actual Cost (Rs/FLAT) | 8791.5 | 22447.938 | 10338.3098

## Slide 19
MAINTENANCE Person In charge – MR. AHUJA SIR
BUDGET 2023-2024 |  | BUDGET |  | 
Sr No | DISCRIPTION | BUDGET | EXPENSES | BALANCE
1. |  |  |  | 
BREAKDOWN REPORT |  | BUDGET | 
Sr No | NAME | NOS OF DAY | NOS OF HOURS
1. |  |  | 
STAFF HIRING 2023-2024 |  | BUDGET | 
Sr No | DESIGNATION | AVAILABLE | REQUIRED
1. |  |  | 

## Slide 20
FUEL EFFICIENCY OF MACHINE |  | BUDGET
Sr No | MACHINE NAME | MACHINE EFFICIENCY
1. |  | 

## Slide 21: Special Mould & Other work Concrete Monthly Summary
 |  |  | THEORETICAL CONCRETE |  |  | ACTUAL CONCRETE |  |  |  | DIFFERENCE | 
Sr | Grade | Unit | ELEMENT | Other Work | Total | COMMON RMC | HCS RMC | Rejected | Total | Difference | %
1. | M10 | CUM |  | 33 | 33 | 33 |  |  | 33 | - | -
2. | M15 | CUM |  | 2 | 2 | 2 |  |  | 2 |  | 
3. | M30 | CUM |  | 46 | 46 | 46 |  |  | 46 | - | -
4. | M40 | CUM | 237 | 13 | 249 | 152 | 114 |  | 266 | 17 | 7
5. | M65 | CUM | 38 |  | 38 |  | 41 |  | 41 | 2 | 6
TOTAL |  | CUM | 275 | 94 | 369 | 233 | 154 | 00 | 388 | 19 | 5

## Slide 22
Pod Factory Concrete Monthly Summary
 |  |  | THEORETICAL CONCRETE |  | ACTUAL CONCRETE |  |  |  |  | DIFFERENCE | 
Sr No | Grade | Unit | Element | Total | Common RMC | HCS RMC | POD RMC | Rejected | TOTAL | Difference | %
1. | M65 | CUM | 2566 | 2566 | 141 | 360 | 2408 | 0 | 2908 | 342 | 13
TOTAL |  | CUM | 2566 | 2566 | 141 | 360 | 2408 | 0 | 2908 | 342 | 13

## Slide 23
 |  |  | THEORETICAL CONCRETE |  |  | ACTUAL CONCRETE |  | DIFFERENCE | 
Sr | Grade | Unit | ELEMENT | Other Work | Total | Reject | Total | Difference | %
1. | M20 | CUM | 72 |  | 72 | 0 | 77 | 5 | 7
2. | M40 | CUM | 353 | 78 | 431 | 0 | 454 | 22 | 5
3. | M25 | CUM | 30 |  | 30 | 0 | 39 | 8 | 28
4. | M65 | CUM | 56 |  | 56 | 0 | 59 | 3 | 5
TOTAL |  | CUM | 511 | 78 | 590 | 0 | 628 | 39 | 7
Carousal Concrete Monthly Summary

## Slide 24
HCS Concrete Monthly Summary
 |  |  | THEORETICAL CONCRETE | ACTUAL CONCRETE |  |  | DIFFERENCE | 
Sr No | Grade | Unit | Element | Reject | Actual | Total | Difference | %
1. | M60 | CUM | 294 |  | 309 | 309 | 15 | 5
TOTAL |  | CUM | 294 | 0 | 309 | 309 | 15 | 5