## Slide 1: Production progress report FTM MAY 24.

## Slide 2: In House Labour Monthly Summary
Sr No | Month | Labour Cost | Concrete | Avg Cost/Cum
1. | April 22 | 2429680 | 544 | 4469
2. | May 22 | 2471217 | 652 | 3788
3. | June 22 | 2813212 | 662 | 4249
4. | July 22 | 2655188 | 400 | 6637
5. | August 22 | 2564097 | 445 | 5761
6. | September 22 | 1990612 | 285 | 6974
7. | October 22 | 2060881 | 387 | 5331
8. | November 22 | 2662365 | 555 | 4801
9. | December 22 | 3995350 | 935 | 4269
10. | January 23 | 4793115 | 972 | 4934
11. | February 23 | 5192192 | 2232 | 2326
12. | March 23 | 4288932 | 903 | 4748
13. | April 23 | 5262161 | 824 | 6384
14. | May 23 | 5668339 | 1006 | 5636
15. | June 23 | 7201632 | 1085 | 6635
16. | July 23 | 4682900 | 506 | 9251
17. | AUGUST 23 | 7961810 | 1316 | 6052

## Slide 3
Sr No | Month | Labour Cost | Concrete | Avg Cost/Cum
17. | AUGUST 23 | 7961810 | 1316 | 6052
18. | SEPTEMBER 23 | 10003410 | 1563 | 6401
19. | OCTOBER 23 | 10370522 | 1342 | 7726
20. | NOVEMBER 23 | 8979301 | 1196 | 7508
21. | DECEMBER 23 | 13128945 | 1863 | 7049
22. | JANUARY 24 | 18989158 | 3224 | 5890
23. | February 24 | 21732402 | 3589 | 6055
24. | March 24 | 22651394 | 3731 | 6072
25. | April 24 | 20895183 | 3008 | 6947
26. | May 24 | 22060451 | 3467 | 6363
In House Labour Monthly Summary

## Slide 4: Special Mould Area. Person in charge – MR. VITRANG
 |  | PLAN FTM MAY 24 |  | ACHIEVED FTM MAY 24 |  |  |  | PLAN FTM JUNE 24 | 
Sr No | Elements | NOS | CUM | NOS | CUM | EXTRA NOS | EXTRA CUM | NOS | CUM
1. | PW | 95 | 334 | 49 | 125 |  |  | 92 | 323
2. | PSS | 60 | 17 | 46 | 14 |  |  | 120 | 35
3. | PB | 99 | 45 | 101 | 49 | 2 | 4 | 149 | 66
4. | PPW |  |  | 2 | 2 | 2 | 2 |  | 
5. | LAN | 10 | 10 | 35 | 33 | 25 | 23 | 11 | 10
TOTAL |  | 264 | 406 | 233 | 224 | 29 | 29 | 372 | 434
 | % |  |  | 88% | 55% |  |  |  | 
Chart: Special Mould Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413
Actual Cost (Rs/cum) | 6630.6668 | 7332.5702 | 4398.3207 | 3721.8117 | 4881.4204 | 5909.2193 | 5914.6348 | 3484.5371
Approved Cost (Rs/cum) | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800

## Slide 5
Element Repairing Person In charge – MR. VITRANG
 |  | PLAN FTM MAY 24 | ACHIEVED FTM MAY 24 | PLAN FTM JUNE 24
Sr No | Element | NOS | NOS | NOS
1. | NLW |  |  | 
2. | PSS |  | 157 | 
3. | PW |  |  | 
4. | PB |  | 268 | 
5. | LAN |  | 34 | 
TOTAL |  |  | 459 | 
Chart: Special Mould Factory Element Repair Cost Performance
| 45413
Actual Cost (Rs/cum) | 758.4376
Approved Cost (Rs/cum) | 500

## Slide 6
Carousal Factory Person In charge – MR. VITRANG
 |  | PLAN FTM MAY 24 |  | ACHIEVED FTM MAY 24 |  |  |  | PLAN FTM JUNE 24 | 
Sr | Elements | NOS | CUM | NOS | CUM | EXTRA NOS | EXTRA CUM | NOS | CUM
1. | NLW | 860 | 371 | 677 | 312 |  |  | 1718 | 717
2. | LS | 369 | 50 | 427 | 58 | 58 | 8 | 628 | 82
3. | PW | 100 | 207 | 74 | 160 |  |  | 182 | 300
4. | LAN | 25 | 15 | 8 | 4 |  |  | 27 | 16
5. | PSS | 14 | 10 | 12 | 11 |  |  | 34 | 26
6. | PPW |  |  | 9 | 4 | 9 | 4 | 4 | 2
7. | Partition Wall |  |  |  |  | 10 | 13 |  | 
TOTAL |  | 1368 | 654 | 1207 | 550 | 77 | 25 | 2593 | 1143
 | % |  |  | 88% | 84% |  |  |  | 
Chart: Carousal Factory Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413
Actual Cost (Rs/cum) | 5630.5074 | 3256.9825 | 6918.8038 | 4313.5078 | 4107.3463 | 5262 | 7417.9145 | 5497.0232
Approved Cost (Rs/cum) | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800

## Slide 7
Element Repairing Person In charge – MR. VITRANG
 |  | PLAN FTM MAY 24 | ACHIEVED FTM MAY 24 | PLAN FTM JUNE 24
Sr No | Element | NOS | NOS | NOS
1. | NLW |  | 71 | 
2. | PSS |  | 2 | 
3. | PW |  | 10 | 
4. | PB |  |  | 
5. | LS |  | 76 | 
TOTAL |  |  | 159 | 
Chart: Carousal Factory Element Repair Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413
Actual Cost (Rs/cum) | 961.8276 | 976.8835 | 1146.4761 | 0 | 1571.1058 | 664.7746 | 1276.5157 | 1466.9766
Approved Cost (Rs/cum) | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500

## Slide 8: Pod Production Person in charge – MR. Rahil
 |  | PLAN FTM MAY 24 |  | ACHIEVED FTM MAY 24 |  |  |  | PLAN FTM JUNE 24 | 
Sr No | Elements | NOS | CUM | NOS | CUM | EXTRA NOS | EXTRA CUM | NOS | CUM
1. | Kitchen POD | 375 | 3226 | 273 | 2133 |  |  | 404 | 3318
2. | Lift POD | 75 | 426 | 63 | 331 | 12 | 95 | 76 | 421
TOTAL |  | 450 | 3652 | 336 | 2464 | 12 | 95 | 480 | 3739
 | % |  |  | 74% | 67% |  |  |  | 
Chart: Pod Factory Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413
Actual Cost (Rs/cum) | 4449.8318 | 3793.9381 | 3754.0823 | 4163.4473 | 4295.0106 | 3691 | 3766.9354 | 3430.1889
Approved Cost (Rs/cum) | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200

## Slide 9
 |  | PLAN FTM MAY 24 |  | ACHIEVED FTM MAY 24 |  | PLAN FTM JUNE 24 | 
Sr No | Elements | NOS | CUM | NOS | CUM | NOS | CUM
1. | HCS | 36BED | 605 | 16BED | 216 | 36BED | 605
 | TOTAL | 36BED | 605 | 16BED | 216 | 36BED | 605
HCS Factory Person In charge – MR. RANA
NOTE - PLAN DEPEND ON BUILDING ERECTION WORK.
Chart: HCS Factory Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413
Actual Cost (Rs/cum) | 3485.2451 | 2596.5348 | 3262.035 | 1632.7197 | 2105.8577 | 2183 | 2318.253 | 2653.1206
Approved Cost (Rs/cum) | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200

## Slide 10: CIVIL Work Person In charge – MR. Gauri.
Sr No | Description | UoM | Qty | Cost/CMT FTM MAY 24
1. | CIVIL WORK | CMT | 7 | 25502

## Slide 11: Element Repairing Person In charge – MR. Sivaraman.
 |  | PLAN FTM MAY 24 | ACHIEVED FTM MAY 24 | PLAN FTM JUNE 24
Sr No | Element | NOS | NOS | NOS
1. | NLW |  |  | 
2. | PB |  | 88 | 
3. | PSS |  | 76 | 
4. | PW |  |  | 
5. | LAN |  |  | 
TOTAL |  | 00 | 164 | 00
Chart: Hospital Area Element Repair Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413
Actual Cost (Rs/cum) | 342.5595 | 548.3994 | 972.0185 | 1647.4268 | 1295.5018 | 1406.1903 | 1426 | 755.2916
Approved Cost (Rs/cum) | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500

## Slide 12: Reinforcement Yard Person In charge – MR. DK Patel.
 |  | PLAN FTM MAY 24 | ACHIEVED FTM MAY 24 | PLAN FTM JUNE 24
Sr No | Element | KGS | KGS | KGS
1. | REINFORCEMENT | 568 | 427 | 628
TOTAL |  | 568 | 427 | 628
 | % |  | 75% | 
Chart: Reinforcement Factory Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413
Actual Cost (Rs/KGS) | 13.9378 | 16.3846 | 11.1359 | 11.1096 | 11.4875 | 8.8383 | 11.8362 | 9.1871
Approved Cost (Rs/KGS) | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12

## Slide 13
POD FINISHING Person In charge – MR. SIVARAMAN.
 |  | PLAN FTM MAY 24 | ACHIEVED FTM MAY 24 | PLAN FTM JUNE 24
Sr No | Element | NOS | NOS | NOS
1. | POD | 350 | 328 | 450
TOTAL |  |  | 328 | 
 | % |  | 94% | 
Chart: Pod Finishing Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413
Actual Cost (Rs/cum) | 2239.73 | 1683.5431 | 2158.2336 | 2432.2128 | 2067.3323 | 2168.5961 | 1855.1424 | 1291.7321
Approved Cost (Rs/cum) | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050 | 1050

## Slide 14
POD ERECTION Person In charge – MR. SIVARAMAN.
 |  | PLAN FTM MAY 24 | ACHIEVED FTM MAY 24 | PLAN FTM JUNE 24
Sr No | Element | NOS | NOS | NOS
1. | POD |  | 220 | 
TOTAL |  |  | 220 | 
 | % |  |  | 
Chart: Pod Erection Cost Performance
| 45323 | 45352 | 45383 | 45413
Actual Cost (Rs/Pod) | 8283.9067 | 6419 | 9138.4767 | 6996.7973
Approved Cost (Rs/Pod) | 4000 | 4000 | 4000 | 4000

## Slide 15
FABRICATION Person In charge – MR. Ramdhyan Yadav
 |  | PLAN FTM MAY 24 | ACHIEVED FTM MAY 24 | PLAN FTM JUNE 24
Sr No | Element | KGS | KGS | KGS
1. | POD(A7 & B2) MODIFICATION FABRICATION WORK |  | 50000 | 
TOTAL |  |  | 50000 | 
 | % |  |  | 
Chart: Fabrication Cost Performance
| 45200 | 45231 | 45261 | 45292 | 45323 | 45352 | 45383 | 45413
Approved Cost (Rs/KGS)
Actual Cost (Rs/KGS) | 14.3433 | 36.5722 | 20.421 | 17.6667 | 28.8746 | 9.2937 | 15 | 14.4495

## Slide 16
BUILDING ERECTION WORK Person In charge – MR. ARUN SIR
CYCLE TIME BUILDING 18 |  | PLAN FTM MAR 24 |  |  |  |  |  |  |  |  |  |  |  |  |  | ACHIEVED FTM APRIL 24 |  |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9 | F10 | F11 | F12 | F13 | F14 | F15 | F16 | F17 | F18 | F19
1. | TYPE1 |  | 11 | 20 | 18 | 15 | 8 | 9 | 10 | 11 | 7 | 19 | 9 | 7 | 9 | 14 | 17 | 19 | 14 | 
2. | TYPE2 |  | 12 | 24 | 14 | 10 | 7 | 13 | 9 | 10 | 6 | 5 | 7 | 10 | 8 | 17 | 15 | 19 | 21 | 14
Chart: POD
| Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | 2023 | 2024 | POD
Total | 28 | 43 | 47 | 83 | 98 | 86 | 77 | 45 | 58

## Slide 17
CYCLE TIME BUILDING 19 |  | PLAN FTM MAR 24 |  |  |  |  |  |  |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9 | F10
1. | TYPE3 |  | 18 | 16 | 16 | 12 | 9 | 21 | 12 | 24 | 16
2. | TYPE4 |  | 21 | 14 | 16 | 23 | 55 |  |  |  | 
3. | TYPE5 |  | 22 | 11 | 15 | 23 | 63 |  |  |  | 
Chart: POD
| Nov | Dec | Jan | Feb | Mar | Apr | May | 2023 | 2024 | POD
Total | 6 | 58 | 47 | 75 | 60 | 48 | 39

## Slide 18
CYCLE TIME BUILDING 14 |  | PLAN FTM MAR 24 |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4
1. | TYPE1 |  |  |  | 
2. | TYPE2 |  |  |  | 
CYCLE TIME BUILDING 16 |  | PLAN FTM MAR 24 |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4
1. | TYPE1 |  |  |  | 
2. | TYPE2 |  |  |  | 
CYCLE TIME BUILDING 15 |  | PLAN FTM MAR 24 |  |  | 
Sr | FLOOR | F1 | F2 | F3 | F4
1. | TYPE1 |  |  |  | 
2. | TYPE2 |  |  |  | 
Chart: POD
| Feb | Mar | Apr | May | POD
Total | 25 | 4 | 19 | 15
Chart: POD
| Feb | Mar | Apr | May | POD
Total | 24 | 10 | 3 | 29
Chart: POD
| Mar | Apr | May | POD
Total | 27 | 5 | 18
Building 14 second Level Screed Completed

## Slide 19
BUILDING FLAT FINISHING WORK Person In charge – MR. ARUN SIR
 |  | PLAN FTM MAY 24 | ACHIEVED FTM MAY 24 | PLAN FTM JUNE 24
Sr No | Element | NOS | NOS | NOS
1. | FLAT | 112 | 80 | 112
TOTAL |  | 112 | 80 | 112
 | % |  | 71% | 
Chart: Flat Finishing Cost Performance
| 45292 | 45323 | 45352 | 45383 | 45413
Actual Cost (Rs/FLAT) | 8791.5 | 22447.938 | 10338 | 8651.2065 | 11843.15
Approved Cost (Rs/FLAT)

## Slide 20
BATCHING PLANT Person In charge – MR. MISHRA
 |  | PLAN FTM MAY 24 | ACHIEVED FTM MAY 24 |  | PLAN FTM JUNE 24
Sr No | Batching Plant | CUM | CUM | EXTRA CUM | CUM
1. | COMMON | 1992 | 1261 |  | 1390
2. | HCS | 1381 | 653 |  | 919
3. | CAROUSAL | 1145 | 588 |  | 1172
4. | POD | 3795 | 1934 |  | 3894
TOTAL |  | 8313 | 4437 |  | 7375
 | % |  | 53% |  | 
Chart: All Batching Plant
| 45413
Approved Cost (Rs/CUM)
Actual Cost (Rs/CUM) COMMON | 74
Actual Cost (Rs/CUM) HCS | 293
Actual Cost (Rs/CUM) CAROUSAL | 149
Actual Cost (Rs/CUM) POD | 50

## Slide 21
MAINTENANCE Person In charge – MR. AHUJA SIR
BUDGET 2023-2024 |  | BUDGET |  | 
Sr No | DISCRIPTION | BUDGET | EXPENSES | BALANCE
1. |  |  |  | 
BREAKDOWN REPORT |  | BUDGET | 
Sr No | NAME | NOS OF DAY | NOS OF HOURS
1. |  |  | 
STAFF HIRING 2023-2024 |  | BUDGET | 
Sr No | DESIGNATION | AVAILABLE | REQUIRED
1. |  |  | 

## Slide 22
FUEL EFFICIENCY OF MACHINE |  | BUDGET
Sr No | MACHINE NAME | MACHINE EFFICIENCY
1. |  | 

## Slide 23: Special Mould & Other work Concrete Monthly Summary
 |  |  | THEORETICAL CONCRETE |  |  | ACTUAL CONCRETE |  |  |  | DIFFERENCE | 
Sr | Grade | Unit | ELEMENT | Other Work | Total | COMMON RMC | HCS RMC | Rejected | Total | Difference | %
1 | M40 | CUM |  | 7 | 7 | 7 |  |  | 7 | - | -
2 | M40 | CUM | 99 |  | 99 | 88 | 20 |  | 108 | 9 | 9
3 | M65 | CUM | 125 |  | 125 | 108 | 25 |  | 133 | 7 | 6
TOTAL |  | CUM | 224 | 7 | 231 | 203 | 44 | 0 | 248 | 16 | 7

## Slide 24
Pod Factory Concrete Monthly Summary
 |  |  | THEORETICAL CONCRETE |  | ACTUAL CONCRETE |  |  |  |  | DIFFERENCE | 
Sr No | Grade | Unit | Element | Total | Common RMC | HCS RMC | POD RMC | Rejected | TOTAL | Difference | %
1 | M65 | CUM | 2464 | 2464 | 329 | 299 | 1934 | 9 | 2553 | 89 | 4
TOTAL |  | CUM | 2464 | 2464 | 329 | 299 | 1934 | 9 | 2553 | 89 | 4

## Slide 25
 |  |  | THEORETICAL CONCRETE |  |  | ACTUAL CONCRETE |  |  | DIFFERENCE | 
Sr | Grade | Unit | ELEMENT | Other Work | Total | Actual | Reject | Total | Difference | %
1 | M20 | CUM | 119 |  | 119 | 127 | 0 | 127 | 7 | 6
2 | M40 | CUM | 78 | 13 | 91 | 96 | 0 | 96 | 5 | 6
3 | M25 | CUM | 192 |  | 192 | 195 | 1 | 193 | 1 | 1
4 | M65 | CUM | 160 |  | 160 | 171 | 1 | 170 | 10 | 6
TOTAL |  | CUM | 550 | 13 | 563 | 588 | 2 | 586 | 23 | 4
May 24 Carousal Concrete Monthly Summary

## Slide 26
MAY 24 HCS Concrete Monthly Summary
 |  |  | THEORETICAL CONCRETE | ACTUAL CONCRETE |  |  | DIFFERENCE | 
Sr No | Grade | Unit | Element | Actual | Rejected | Total | Difference | %
1 | M60 | CUM | 216 | 249 | 4 | 245 | 29 | 14
TOTAL |  | CUM | 216 | 249 | 4 | 245 | 29 | 14