## Slide 1: Production progress report FTM NOVEMBER 23.

## Slide 2: In House Labour Monthly Summary
Sr No | Month | Labour Cost | Concrete | Avg Cost/Cum
1. | April 22 | 2429680.2 | 543.72 | 4468.623942
2. | May 22 | 2471216.7 | 652.44 | 3787.653629
3. | June 22 | 2813211.5 | 662.05 | 4249.243305
4. | July 22 | 2655187.5 | 400.03 | 6637.47094
5. | August 22 | 2564097.2 | 445.05 | 5761.368783
6. | September 22 | 1990611.5 | 285.44 | 6973.834985
7. | October 22 | 2060881 | 386.6 | 5330.783756
8. | November 22 | 2662365 | 554.5425 | 4801.011645
9. | December 22 | 3995349.8 | 935.449 | 4268.789227
10. | January 23 | 4793114.919 | 971.5238 | 4933.605248
11. | February 23 | 5192192 | 2232.18 | 2326.0633
12. | March 23 | 4288932 | 903.2691 | 4748.232835
13. | April 23 | 5262161.03 | 824.24 | 6384.3
14. | May 23 | 5668339.00 | 1005.79 | 5635.70824
15. | June 23 | 7201632.00 | 1085.3411 | 6635.362836
16. | July 23 | 4682900.0 | 506.18 | 9251.45
17. | AUGUST 23 | 7961810.00 | 1315.51 | 6052.26
18. | SEPTEMBER 23 | 10003410.00 | 1562.67 | 6401.48
19. | OCTOBER 23 | 9365546.39 | 1318.24 | 7104.58
20. | NOVEMBER 23 | 7006222.98 | 1185.77 | 5908.58

## Slide 3: Special Mould Area. Person in charge – MR. Arbab
Sr No | Elements | Total Elements to be casted | Planned FTM November 23 | Concrete FTM November 23 | Achieved FTM November 23 | Concrete Consumed | Unplanned Element | Unplanned Concrete | Produced Element | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM November 23
1. | PW | 3129 | 126 | 258.7 | 56 | 103.77 | 0 | 0 | 969 | 2160 | 54 | 170.55 |  | 
2. | PSS | 5862 | 30 | 13.989 | 11 | 2.89 | 0 | 0 | 3650 | 2212 | 0 | 0 |  | 
3. | PB | 2806 | 5 | 1.34 | 48 | 19.96 | 43 | 18.62 | 1963 | 843 | 11 | 4.55 |  | 
4. | COUNTER WEIGHT |  |  |  |  |  | 4 | 4.48 |  |  |  |  |  | 
5. | LAN | 920 | 69 | 38 | 47 | 44.65 | 0 | 0 | 368 | 552 | 26 | 23.75 |  | 
TOTAL |  | 11889 | 230 | 312.029 | 162 | 171.27 | 47 | 23.1 | 6950 | 5767 | 91 | 198.85 | 1800 | 7,332.57

## Slide 4: Pod Production Person in charge – MR. Rahil
Sr No | Elements | Total Elements to be casted | Plan FTM November 23 | Concrete FTM November 23 | Achieved FTM November 23 | Concrete Consumed | Unplanned Element | Unplanned Concrete | Produced Element | Balance to cast | Plan For Next Month | Concrete Consumption for next month | Approved Cost/CMT | Cost/CMT FTM November 23
1. | Kitchen POD - 1 | 217 | 18 | 136.08 | 12 | 90.72 |  |  | 180 | 37 | 1 | 7.56 |  | 
2. | Kitchen POD - 2 | 453 | 0 | 00 |  |  |  |  | 194 | 259 |  |  |  | 
3. | Lift POD | 92 | 18 | 80.38 | 25 | 111.15 |  |  | 35 | 57 | 14 | 105.84 |  | 
4. | LTKP - 1 | 60 | 26 | 196.56 | 18 | 136.08 |  |  | 23 | 37 | 14 | 105.84 |  | 
5. | LTKP - 2 | 60 | 42 | 317.52 | 30 | 226.8 |  |  | 34 | 26 | 3 | 22.68 |  | 
6. | LTKP – 3 | 30 | 5 | 37.8 | 10 | 75.6 | 5 | 37.8 | 10 | 20 | 7 | 52.92 |  | 
7. | LTKP - 4 | 30 | 5 | 37.8 | 3 | 22.68 |  |  | 3 | 27 | 16 | 120.96 |  | 
8. | RKP - 1 | 4 | 4 | 30.24 |  |  |  |  | 4 | 0 |  |  |  | 
9. | MTKP - 3 | 6 | 4 | 30.24 |  |  |  |  | 4 | 2 | 1 | 7.56 |  | 
10. | Kitchen POD – 101/102 | 140 | 48 | 141.44 | 7 | 61.88 |  |  | 13 | 127 | 32 | 282.88 |  | 
11. | Lift POD 101/102/103/104 | 176 |  |  |  |  |  |  |  | 176 |  |  |  | 
12. | Kitchen pod FKP-01/02 | 72 |  |  |  |  |  |  | 36 | 36 | 10 | 64 |  | 
TOTAL |  | 1340 | 108 | 834.76 | 105 | 724.91 | 5 | 37.8 | 536 | 804 | 98 | 770.24 | 2200 | 3,793.94

## Slide 5: Precast Factory STP Tank Work Person In charge – MR. Gauri.
Sr No | Description | UoM | Qty | Cost/CMT FTM November 23
1. | STP TANK WORK | CMT | 10 | 6,753.25

## Slide 6: Element Repairing Person In charge – MR. Sivaraman.
Sr No | Element/Description | Planned FTM November 23 | Achieved FTM November 23 | Plan For Next Month | Approved Cost/CMT | Cost/CMT FTM November 23 | Remarks
1. | Element Handover | 00 | 104 | 00 | 500 | 548.40 | 
Element Repairing Person In charge – MR. Amardeep
Sr No | Element/Description | Planned FTM November 23 | Achieved FTM November 23 | Plan For Next Month | Approved Cost/CMT | Cost/CMT FTM November 23 | Remarks
1. | Element Handover | 00 | 189 | 00 | 500 | 976.88 | 

## Slide 7: Reinforcement Yard Person In charge – MR. DK Patel.
Sr No | Element/Description | Planned FTM November 23 | Achieved FTM November 23 | Plan For Next Month | Approved Cost/KG | Cost/KG, MTT FTM November 23 | Remarks
1. | Reinforcement | 295.63 MTT | 109.12 MTT | 190.70MTT | 15 | 16.38 | 

## Slide 8
POD FINISHING Person In charge – MR. SIVARAMAN.
Sr No | Element/Description | Planned FTM November 23 | Achieved FTM November 23 | Plan For Next Month | Approved Cost/CUM | Cost/CUM FTM November 23 | Remarks
1. | Element Handover | 70 | 83 | 80 | 1050 | 1,683.54 | 
POD FINISHING Person In charge – MR. AMARDEEP
Sr No | Element/Description | Planned FTM November 23 | Achieved FTM November 23 | Plan For Next Month | Approved Cost/CUM | Cost/CUM FTM November 23 | Remarks
1. | Element Handover |  | 10 |  | 1050 |  | 

## Slide 9
Carousal Factory Person In charge – MR. AMARDEEP
Sr No | Elements | Total Elements to be casted | Planned FTM November 23 | Concrete FTM November 23 | Achieved FTM November 23 | Concrete Consumed | Unplanned Element | Unplanned Element | Produced Element | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM November 23
1. | NLW | 23034 | 1060 | 492.27 | 143 | 93.38 |  |  | 9667 | 13367 | 671 | 301.83 |  | 
2. | LS | 10500 | 50 | 11.66 |  |  |  |  | 5829 | 4671 | 00 | 00 |  | 
3. | PW | 3129 | 188 | 298.03 | 28 | 33.96 |  |  | 969 | 2160 | 47 | 51.48 |  | 
4. | LAN | 920 | 32 | 16.32 | 14 | 7.14 |  |  | 368 | 552 | 24 | 12.24 |  | 
5. | PSS | 5862 | 54 | 55.79 | 19 | 21.34 |  |  | 3650 | 2212 | 17 | 10.54 |  | 
6. | TRENCH SLAB |  |  |  |  |  | 28 | 5.32 |  |  |  |  |  | 
TOTAL |  |  | 1384 | 874.07 | 204 | 155.82 | 28 | 5.32 | 20483 | 22962 | 759 | 376.09 | 1800 | 3,256.98

## Slide 10
Sr No | Elements | Total Elements to be casted | Planned FTM November 23 | Concrete FTM November 23 | Achieved FTM November 23 | Concrete Consumed | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM November 23
1. | HCS |  | 18.5 BED | 329.66 | 9 BED | 133.78 |  | 11.6 BED | 212.05 |  | 2,596.53
HCS Factory Person In charge – MR. RANA

## Slide 11
Sr No | Element/Description | Planned FTM November 23 | Achieved FTM November 23 | Plan For Next Month | Approved Cost/KGS | Cost/CMT FTM November 23 | Remarks
1. | STEEL FABRICATION | 00 | 12.529MTT | 00 | 00 | 36.57 | 
FABRICATION Person In charge – MR. Ramdhyan Yadav

## Slide 12: Special Mould & Pod Factory & Other work Concrete Monthly Summary
Sr No | Grade | Unit | Theoretical Concrete (Element) | Cover Drain and other activities | Total Theoretical | Actual OLD RMC Concrete | Actual HCS RMC Concrete | POD BATCHING PLANT | Concrete Rejected | TOTAL OLD RMC & HCS RMC & POD RMC ACTUAL CONCRETE | Difference (Actual – Theoretical) | Difference %
1. | M10 | CUM | 0 | 2 | 2 | 2 | - | - | 00 | 2 | - | -
2. | M30 | CUM | 0 | 00 | 00 | 00 |  | - | 00 | 00 | - | -
3. | M40 | CUM | 67.5 | 12.48 | 79.98 | 21.7 | 63.8 | - | 00 | 85.5 | 5.52 | 6.90
4. | M65 | CUM | 828.68 | 0 | 828.68 | 88 | 398.6 | 472.8 | 22.5 | 936.9 | 108.2 | 13.05
TOTAL |  | CUM | 896.18 | 14.48 | 910.66 | 111.7 | 462.4 | 472.8 | 22.5 | 1024.4 | 113.74 | 12.48

## Slide 13
Sr No | Grade | Unit | Theoretical Concrete (Element) | Other Work concrete | Total Theoretical Concrete | Reject Concrete | Total Actual Concrete | Difference (Actual – Theoretical) | Difference %
1. | M20 | CUM | 80.30 |  | 80.30 | 00 | 86.95 | 6.65 | 8.28
2. | M40 | CUM | 41.56 | 5.32 | 46.88 | 00 | 48.1 | 1.22 | 2.60
3. | M65 | CUM | 33.96 |  | 33.96 | 00 | 34.75 | 0.79 | 2.32
TOTAL |  | CUM |  |  | 161.14 | 00 | 169.8 | 8.66 | 5.37
Carousal Concrete Monthly Summary

## Slide 14
NOVEMBER 23 HCS Concrete Monthly Summary
Sr No | Grade | Unit | Theoretical Concrete (Element) | Reject Concrete | Actual Concrete | Total actual Concrete | Difference (Actual – Theoretical | Difference %
1. | M60 | CUM | 133.78 | 1 | 143.1 | 142.1 | 8.32 | 6.21
TOTAL |  | CUM |  |  | 143.1 | 142.1 | 8.32 | 6.21