## Slide 1: Production progress report FTM OCTOBER 23.

## Slide 2: In House Labour Monthly Summary
Sr No | Month | Labour Cost | Concrete | Avg Cost/Cum
1. | April 22 | 2429680.2 | 543.72 | 4468.623942
2. | May 22 | 2471216.7 | 652.44 | 3787.653629
3. | June 22 | 2813211.5 | 662.05 | 4249.243305
4. | July 22 | 2655187.5 | 400.03 | 6637.47094
5. | August 22 | 2564097.2 | 445.05 | 5761.368783
6. | September 22 | 1990611.5 | 285.44 | 6973.834985
7. | October 22 | 2060881 | 386.6 | 5330.783756
8. | November 22 | 2662365 | 554.5425 | 4801.011645
9. | December 22 | 3995349.8 | 935.449 | 4268.789227
10. | January 23 | 4793114.919 | 971.5238 | 4933.605248
11. | February 23 | 5192192 | 2232.18 | 2326.0633
12. | March 23 | 4288932 | 903.2691 | 4748.232835
13. | April 23 | 5262161.03 | 824.24 | 6384.3
14. | May 23 | 5668339.00 | 1005.79 | 5635.70824
15. | June 23 | 7201632.00 | 1085.3411 | 6635.362836
16. | July 23 | 4682900.0 | 506.18 | 9251.45
17. | AUGUST 23 | 7961810.00 | 1315.51 | 6052.26
18. | SEPTEMBER 23 | 10003410.00 | 1562.67 | 6401.48
19. | OCTOBER 23 | 9365546.39 | 1318.24 | 7104.58

## Slide 3: Special Mould Area. Person in charge – MR. Irfan/Arbab.
Sr No | Elements | Total Elements to be casted | Planned FTM October 23 | Concrete FTM October 23 | Achieved FTM October 23 | Concrete Consumed | Unplanned Element | Unplanned Concrete | Produced Element | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM October 23
1. | PW | 3129 | 146 | 422.77 | 15 | 37.37 | 0 | 0 | 885 | 2244 | 97 | 175.39 |  | 
2. | PSS | 5862 | 21 | 6.19 | 334 | 118.31 | 313 | 112.15 | 3620 | 2242 | 28 | 13.363 |  | 
3. | PB | 2806 | 219 | 97.76 | 134 | 36.26 |  |  | 1915 | 891 |  |  |  | 
4. | POD BEAM, ETP |  |  |  |  |  | 34 | 20.45 |  |  |  |  |  | 
5. | LAN | 920 | 49 | 19 | 20 | 19 |  |  | 307 | 613 | 52 | 49.4 |  | 
TOTAL |  | 11889 | 435 | 545.72 | 503 | 210.94 | 347 | 132.6 | 6727 | 5990 | 177 | 238.153 | 1800 | 6630.67

## Slide 4: Pod Production Person in charge – MR. Rahil
Sr No | Elements | Total Elements to be casted | Plan FTM October 23 | Concrete FTM October 23 | Achieved FTM October 23 | Concrete Consumed | Unplanned Element | Unplanned Concrete | Produced Element | Balance to cast | Plan For Next Month | Concrete Consumption for next month | Approved Cost/CMT | Cost/CMT FTM October 23
1. | Kitchen POD - 1 | 217 | 66 | 498.96 | 17 | 128.52 |  |  | 168 | 49 | 16 | 120.96 |  | 
2. | Kitchen POD - 2 | 453 | 7 | 52.92 | 10 | 75.60 | 3 | 22.68 | 194 | 259 |  |  |  | 
3. | Lift POD | 92 |  |  | 17 | 76.77 | 17 | 76.77 | 78 | 14 |  |  |  | 
4. | LTKP - 1 | 60 |  |  | 5 | 37.80 | 5 | 37.80 | 5 | 55 | 16 | 120.96 |  | 
5. | LTKP - 2 | 60 |  |  | 4 | 30.24 | 4 | 30.24 | 4 | 56 | 32 | 241.92 |  | 
6. | RKP - 2 | 4 |  |  | 4 | 30.24 | 4 | 30.24 | 4 | 0 |  |  |  | 
7. | Kitchen POD – 101/102 | 140 | 32 | 282.88 | 0 | 00 |  |  | 6 | 136 | 32 | 282.88 |  | 
8. | Lift POD 101/102/103/104 | 176 |  |  |  |  |  |  |  | 176 |  |  |  | 
9. | Kitchen pod FKP-01/02 | 72 |  |  | 22 | 122.02 |  |  | 36 | 36 |  |  |  | 
TOTAL |  |  | 108 | 834.76 | 79 | 501.19 | 33 | 197.73 | 495 | 781 | 86 | 766.72 | 2200 | 4449.83

## Slide 5: Precast Factory ETP TANK & TOWER CRANE FOUNDATION WORK Person In charge – MR. Gauri.
Sr No | Description | UoM | Qty | Cost/CMT FTM October 23
1. | ETP TANK & TOWER CRANE FOUNDATION WORK | CMT | 173.5 | 262.99
2. | SCREED SLAB | CMT | 103 | 

## Slide 6: Element Repairing Person In charge – MR. Sivaraman.
Sr No | Element/Description | Planned FTM October 23 | Achieved FTM October 23 | Plan For Next Month | Approved Cost/CMT | Cost/CMT FTM October 23 | Remarks
1. | Element Handover | 00 | 32 | 00 | 500 | 342.56 | 
Element Repairing Person In charge – MR. Amardeep
Sr No | Element/Description | Planned FTM October 23 | Achieved FTM October 23 | Plan For Next Month | Approved Cost/CMT | Cost/CMT FTM October 23 | Remarks
1. | Element Handover | 00 | 96 | 00 | 500 | 961.83 | 

## Slide 7: Reinforcement Yard Person In charge – MR. DK Patel.
Sr No | Element/Description | Planned FTM October 23 | Achieved FTM October 23 | Plan For Next Month | Approved Cost/KG | Cost/KG, MTT FTM October 23 | Remarks
1. | Reinforcement | 215.841MTT | 159.745 MTT |  | 15 | 13.94 | 

## Slide 8
POD FINISHING Person In charge – MR. SIVARAMAN.
Sr No | Element/Description | Planned FTM October 23 | Achieved FTM October 23 | Plan For Next Month | Approved Cost/CUM | Cost/CUM FTM October 23 | Remarks
1. | Element Handover | 60 | 50 | 70 | 1050 | 2239.73 | 

## Slide 9
Carousal Factory Person In charge – MR. AMARDEEP
Sr No | Elements | Total Elements to be casted | Planned FTM October 23 | Concrete FTM October 23 | Achieved FTM October 23 | Concrete Consumed | Unplanned Element | Unplanned Element | Produced Element | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM October 23
1. | NLW | 23034 | 218 | 80.99 | 333 | 220.14 | 115 | 139.15 | 9524 | 13510 | 611 | 297.43 |  | 
2. | LS | 10500 | 80 | 12.72 | 132 | 20.34 | 52 | 7.62 | 5829 | 4671 | 50 | 11.66 |  | 
3. | PW | 3129 | 98 | 231.33 | 82 | 144.94 |  |  | 885 | 2244 | 131 | 220.3 |  | 
4. | LAN | 920 | 18 | 9.1 | 27 | 13.81 | 9 | 4.71 | 307 | 613 | 32 | 16.32 |  | 
5. | PSS | 5862 | 27 | 28.50 | 37 | 42.98 | 10 | 14.48 | 3620 | 2242 | 32 | 32.592 |  | 
6. | COUNTER WEIGHT & TRENCH SLAB |  |  |  |  |  | 9 | 3.62 |  |  |  |  |  | 
TOTAL |  |  | 441 | 362.64 | 611 | 442.21 | 195 | 169.58 | 20165 | 23280 | 856 | 578.302 | 1800 | 5630.51

## Slide 10
Sr No | Elements | Total Elements to be casted | Planned FTM October 23 | Concrete FTM October 23 | Achieved FTM October 23 | Concrete Consumed | Balance to cast | Plan For Next Month | Concrete Plan for Next month | Approved Cost/CMT | Cost/CMT FTM October 23
1. | HCS | 5544 |  |  | 347 | 163.90 |  | 11.6 BED | 206.71 |  | 3485.25
HCS Factory Person In charge – MR. RANA

## Slide 11
Sr No | Element/Description | Planned FTM October 23 | Achieved FTM October 23 | Plan For Next Month | Approved Cost/KGS | Cost/CMT FTM October 23 | Remarks
1. | STEEL FABRICATION | 00 | 27.113MTT | 00 | 00 | 14.34 | 
FABRICATION Person In charge – MR. Ramdhyan Yadav

## Slide 12: Special Mould & Pod Factory & Other work Concrete Monthly Summary
Sr No | Grade | Unit | Theoretical Concrete (Element) | Cover Drain and other activities | Total Theoretical | Actual OLD RMC Concrete | Actual HCS RMC Concrete | POD BATCHING PLANT | Concrete Rejected | TOTAL OLD RMC & HCS RMC & POD RMC ACTUAL CONCRETE | Difference (Actual – Theoretical) | Difference %
1. | M10 | CUM | 0 | 22 | 22 | 22 | - | - | 00 | 22 | - | -
2. | M30 | CUM | 0 | 1.5 | 1.5 | 1.5 | 1.5 | - | 00 | 1.5 | - | -
3. | M40 | CUM | 173.57 | 299.45 | 473.02 | 289.4 | 205 | - | 00 | 494.4 | 21.38 | 4.51
4. | M65 | CUM | 538.56 | 9 | 547.56 | 184 | 62.2 | 355.4 | 7.9 | 593.7 | 46.14 | 8.42
TOTAL |  | CUM | 712.13 | 331.95 | 1044.08 | 496.9 | 268.7 | 355.4 | 7.9 | 1111.6 | 67.52 | 6.46

## Slide 13
Sr No | Grade | Unit | Theoretical Concrete (Element) | Other Work concrete | Total Theoretical Concrete | Reject Concrete | Total Actual Concrete | Difference (Actual – Theoretical) | Difference %
1. | M20 | CUM | 211.25 |  | 211.25 | 00 | 228.9 | 17.65 | 8.35
2. | M40 | CUM | 86.02 | 3.62 | 89.64 | 00 | 95.45 | 5.81 | 6.48
3. | M65 | CUM | 144.94 |  | 144.94 | 00 | 148.2 | 3.26 | 2.24
TOTAL |  | CUM |  |  | 445.83 | 00 | 472.55 | 26.72 | 5.99
Carousal Concrete Monthly Summary

## Slide 14
OCTOBER 23 HCS Concrete Monthly Summary
Sr No | Grade | Unit | Theoretical Concrete (Element) | Reject Concrete | Actual Concrete | Total actual Concrete | Difference (Actual – Theoretical | Difference %
1. | M60 | CUM | 163.90 | 1 | 188.9 | 187.9 | 24 | 14.64
TOTAL |  | CUM |  |  | 188.9 | 187.9 | 24 | 14.64